## Dashboard
CortexKitchen Project Dashboard
Current milestone | Phase 1 — Merged to Dev
Last completed branch | feature/phase1-tests
Current stable branches | main synced with Phase 1; dev active
Next recommended branch | phase 2
Flagship demo | Friday Night Rush Optimization
Phase | Status | % Complete | Key outcome
Phase 0 | Completed | 100% | Docs, roadmap, architecture, data model, APIs, evaluation, implementation plan
Phase 1 | Completed | 100% | API + Docker + DB + Seed + LLM + Core services + Qdrant complete+ langgraph skeleton + friday rush endpoint; dashboard complete; tests done
Phase 2 | Not started | 0% | Optimization layer
Phase 3 | Not started | 0% | Advanced agentic features

## Phase Tracker
Phase | Order | Task ID | Workstream | Task | Detailed outcome / done means | Branch | Status | Priority | Owner | Start date | Target date | Done date | Progress % | Depends on | Tests expected | PR / Notes
Phase 0 | 1 | P0-01 | Repo | Create repo + branches | GitHub repo created, main/dev set up, no direct work on main | feature/phase0-repo-scaffold | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% |  | Smoke check repo + branch flow | Merged to dev, later synced to main
Phase 0 | 2 | P0-02 | Docs | PRD + roadmap + decisions | Core product direction locked in docs | feature/phase0-architecture-docs | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-01 | Doc review | Merged to dev, branch deleted
Phase 0 | 3 | P0-03 | Docs | Architecture doc | System layers, flow, LLM/RAG strategy captured | feature/phase0-architecture | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-02 | Doc review | Merged to dev, branch deleted
Phase 0 | 4 | P0-04 | Docs | Agents + data model + APIs | Agent specs, DB model, API contracts documented | feature/phase0-agents-data-api | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-03 | Doc review | Merged to dev, branch deleted
Phase 0 | 5 | P0-05 | Docs | Evaluation + implementation plan | Evaluation rubric and build order finalized | feature/phase0-evaluation-plan | Completed | High | Anoushka | 2026-03-15 | 2026-03-16 | 2026-03-16 | 100% | P0-04 | Doc review | Merged to dev, branch deleted
Phase 0 | 6 | P0-06 | Release | Sync dev to main | Stable milestone branch updated with Phase 0 foundation | dev -> main PR | Completed | High | Anoushka | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | P0-05 | Milestone verification | Main synced
Phase 1 | 7 | P1-01 | Backend | API scaffold | FastAPI app boots, settings, health endpoints, dependency checks, tests pass | feature/phase1-api-scaffold | Completed | High | Anoushka | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | P0-06 | 3 unit tests + manual endpoint verification | Root, docs, /health, /health/dependencies verified
Phase 1 | 8 | P1-02 | Infra | Docker infra | docker-compose for Postgres, Qdrant, Redis; startup verified | feature/phase1-infra-docker | Completed | High | Anoushka | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | P1-01 | Service startup smoke tests | Merged to dev, branch deleted
Phase 1 | 9 | P1-03 | Backend | DB schema + models | Initial relational schema for reservations, orders, complaints, traces | feature/phase1-db-schema | Completed | High | Anoushka | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | P1-02 | Schema tests / migrations sanity | Merged to dev, branch deleted
Phase 1 | 10 | P1-04 | Data | Seed data | Pizza-heavy synthetic data with Friday spikes and simulated reservation/review sources | feature/phase1-seed-data | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-03 | Seed script smoke tests | Merged to dev, branch deleted
Phase 1 | 11 | P1-05 | Backend | LLM provider layer | Base provider + Gemini provider + prompt utilities | feature/phase1-llm-provider | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-01 | Provider unit/integration tests | Merged to dev, branch deleted
Phase 1 | 12 | P1-06 | Backend | Core services | Reservation analytics, baseline forecast, complaint summary, critic rules | feature/phase1-core-services | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-03 | Unit tests for services/rules | Merged to dev, branch deleted
Phase 1 | 13 | P1-07 | Memory | Qdrant memory | Collections, embeddings, retrieval helpers for complaints/SOPs | feature/phase1-qdrant-memory | Completed | Medium | Anoushka | 2026-04-05 | 2026-04-05 | 2026-04-05 | 100% | P1-02, P1-05 | Integration tests with retrieval | Merged to dev, branch deleted
Phase 1 | 14 | P1-08 | Agents | LangGraph skeleton | Shared state, nodes, graph edges, stub flow | feature/phase1-langgraph-skeleton | Completed | High | Anoushka | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | P1-05, P1-06 | Graph flow tests | Merged to dev, branch deleted
Phase 1 | 15 | P1-09 | Backend | Friday rush endpoint | End-to-end planning endpoint + aggregated recommendation + trace write | feature/phase1-friday-rush-endpoint | Completed | High | Anoushka | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | P1-06, P1-07, P1-08 | Integration + manual demo test | Merged to dev, branch deleted
Phase 1 | 16 | P1-10 | Frontend | Dashboard MVP | Planning result UI with forecast, complaint, critic, trace sections | feature/phase1-dashboard | Completed | Medium | Anoushka | 2026-04-10 | 2026-04-11 | 2026-04-11 | 100% | P1-09 | Frontend smoke tests | Merged to dev, branch deleted
Phase 1 | 17 | P1-11 | Quality | Phase 1 tests | Unit + integration + first E2E Friday rush flow | feature/phase1-tests | Completed | High | Anoushka | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | P1-09, P1-10 | Pytest + scenario checklist | Merged to dev, branch deleted
Phase 1 | 18 | P1-12 | Release | Sync Phase 1 to main | Stable MVP milestone on main | dev -> main PR | Completed | High | Anoushka | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | P1-11 | Milestone verification | Main synced
Phase 2 | 19 | P2-01 | Forecasting | Prophet upgrade | Replace/add baseline with Prophet forecasting path | feature/phase2-prophet-upgrade | Planned | Medium | Anoushka |  |  |  | 0.0 | P1-12 | Forecast comparison tests
Phase 2 | 20 | P2-02 | Ops | Inventory alerts | Shortage/overstock alerts using forecast + stock levels | feature/phase2-inventory-alerts | Planned | Medium | Anoushka |  |  |  | 0.0 | P2-01 | Rule tests
Phase 2 | 21 | P2-03 | Menu | Menu insights | Top/weak items and promo suggestions surfaced in API/UI | feature/phase2-menu-insights | Planned | Medium | Anoushka |  |  |  | 0.0 | P1-12 | Analytics tests
Phase 2 | 22 | P2-04 | Frontend | Dashboard enhancement | Richer analytics and clearer operational panels | feature/phase2-dashboard-enhancement | Planned | Medium | Anoushka |  |  |  | 0.0 | P2-02, P2-03 | Frontend checks
Phase 2 | 23 | P2-05 | Quality | Evaluation refinement | Stronger manual rubric + automated quality checks | feature/phase2-evaluation-refinement | Planned | Low | Anoushka |  |  |  | 0.0 | P2-01, P2-02, P2-03 | Eval checks
Phase 2 | 24 | P2-06 | Release | Sync Phase 2 to main | Optimization milestone | dev -> main PR | Planned | Medium | Anoushka |  |  |  | 0.0 | P2-05 | Milestone verification
Phase 3 | 25 | P3-01 | Agents | Debate/review loop | Proposal-review or debate flow between agents | feature/phase3-debate-loop | Planned | Low | Anoushka |  |  |  | 0.0 | P2-06 | Flow tests
Phase 3 | 26 | P3-02 | Scoring | Cost-aware scoring | Recommendation scoring with cost/benefit awareness | feature/phase3-cost-aware-scoring | Planned | Low | Anoushka |  |  |  | 0.0 | P3-01 | Rule tests
Phase 3 | 27 | P3-03 | Memory | Decision memory reuse | Past decision summaries used in planning context | feature/phase3-decision-memory | Planned | Low | Anoushka |  |  |  | 0.0 | P3-01 | Retrieval tests
Phase 3 | 28 | P3-04 | Quality | Advanced critic | Richer critic scoring and revision feedback | feature/phase3-advanced-critic | Planned | Low | Anoushka |  |  |  | 0.0 | P3-02 | Critic tests
Phase 3 | 29 | P3-05 | Release | Sync Phase 3 to main | Advanced milestone | dev -> main PR | Planned | Low | Anoushka |  |  |  | 0.0 | P3-04 | Milestone verification

## Git Practices
Git / Branching Rules
Branch | Purpose | Rule | Current note
main | Stable milestone only | Only sync from dev when a phase milestone is safe/demo-ready | Phase 0 already synced
dev | Active integration branch | All merged feature work lands here first | Current working base
feature/... | All implementation and docs work | Create from latest dev, PR back to dev, then delete branch | Current style
Local cleanup | After merge | Delete remote + local feature branch, checkout dev, pull latest | Continue throughout project