## Sheet1
CortexKitchen Project Dashboard | Unnamed: 1 | Unnamed: 2 | Unnamed: 3
Current milestone | Phase 2 — Prophet Upgrade Completed
Last completed branch | feature/phase2-prophet-upgrade
Current stable branches | main synced with Phase 1; dev active
Next recommended branch | phase 3
Flagship demo | Friday Night Rush Optimization
Phase | Status | % Complete | Key outcome
Phase 0 | Completed | 1 | Docs, roadmap, architecture, data model, APIs, evaluation, implementation plan
Phase 1 | Completed | 1 | API + Docker + DB + Seed + LLM + Core services + Qdrant complete+ langgraph skeleton + friday rush endpoint; dashboard complete; tests done
Phase 2 | Completed | 1 | Optimization layer
Phase 3 | Not started | 0 | Advanced agentic features