## Dashboard
CortexKitchen — Project Dashboard
Current milestone: Phase 6 -- P6-S35-S42/S47/S48 (this branch's hardening fixes) complete; inventory now cites live Swiggy Instamart prices end-to-end, replan loop + critic converge to approved on first pass. Next: P6-MI01-04 (market intel expansion) or P6-S43-S46 (follow-ups). | 35 of 62 Phase 6 tasks done. Staging-blocked work + docs/milestone-merge + Phase 7 now tracked separately in the 'Staging Creds + Phase 7' sheet.
Last completed: P6-S48 -- Windows console-encoding crash fix (was silently 500ing every planning run) | P6-S42 rewritten to reflect the real bug found (inventory price-ordering + guardrail discarding the Swiggy citation, not the originally-planned occupancy-context gap); P6-S47 resolved (AGENTS.md injected line removed per user decision). All live-verified end to end, including a Playwright check that the Swiggy price citation renders correctly in the actual /runs UI.
Build order: S07/S08/S09 (enrichers) → S10-S13 (new nodes + diffs) → F04/F06 (frontend) → S14 (action queue) → F01/F02 → S15/S16 | SWIGGY_INTEGRATION.md now has response schemas (section 16) + tool→DB mapping table (section 17)
Staging creds status | Pending from Swiggy. Needed ONLY for checkout + book_table (P6-S30, P6-S31). Everything else works with production OAuth token.
Phase | Status | % Complete | Key outcome
Phase 0 | Completed | 1 | Docs, roadmap, architecture, data model, APIs, evaluation, implementation plan
Phase 1 | Completed | 1 | API + Docker + DB + Seed + LLM + Core services + Qdrant complete+ langgraph skeleton + friday rush endpoint; dashboard complete; tests done
Phase 2 | Completed | 1 | Optimization layer: Prophet forecasting, inventory alerts, menu insights, and dashboard enhancementand evaluation refinement complete
Phase 3 | Completed | 1 | Advanced agentic features: auditable planning runs, richer critic evaluation, cost-aware scoring, and multi-scenario operational planning
Phase 4 | Completed | 1 | Productisation (no real data required): auth, LangSmith tracing, health checks, structured logging, LLM cost tracking, admin UI, runs UI, restaurant profiles, LLM provider swap, RAGAS evals, DeepEval, MCP server
Phase 5 | Completed | 1 | PDF/Excel export, frontend UX fixes, Redis cache, SSE streaming, what-if simulator, observability, evals, tenant isolation, email digest, RAG chatbot
Phase 6 | In Progress | 56.45% | Swiggy-native restaurant OS: connector layer (Swiggy first, POS second), 11-node LangGraph pipeline, action queue with approval gates, 3 product modes (ops/brief/live), voice interface, 5 new frontend pages
Phase 7 | Planned | 0 | Production deploy: CI/CD, Railway/Fly.io, managed Postgres+Redis, production hardening, public release

## Phase Tracker ( 1 - 5 )
CortexKitchen — Phase Tracker (P0 through P6-S06 complete)
Phase 6 planned tasks (P6-01 onwards) live in the Phase 6 sheet · This sheet = historical record only
Phase | Order | Task ID | Workstream | Task | Detailed Outcome / Done Means | Branch | Status | Priority | Owner | Start | Target | Done | Progress % | Depends On | Tests Expected | PR / Notes
Phase 0
Phase 0 | 1 | P0-01 | Repo | Create repo + branches | GitHub repo created, main/dev set up, no direct work on main | feature/phase0-repo-scaffold | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% |  | Smoke check repo + branch flow | Merged to dev, later synced to main
Phase 0 | 2 | P0-02 | Docs | PRD + roadmap + decisions | Core product direction locked in docs | feature/phase0-architecture-docs | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-01 | Doc review | Merged to dev, branch deleted
Phase 0 | 3 | P0-03 | Docs | Architecture doc | System layers, flow, LLM/RAG strategy captured | feature/phase0-architecture | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-02 | Doc review | Merged to dev, branch deleted
Phase 0 | 4 | P0-04 | Docs | Agents + data model + APIs | Agent specs, DB model, API contracts documented | feature/phase0-agents-data-api | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-03 | Doc review | Merged to dev, branch deleted
Phase 0 | 5 | P0-05 | Docs | Evaluation + implementation plan | Evaluation rubric and build order finalized | feature/phase0-evaluation-plan | Completed | High | Anoushka | 2026-03-15 | 2026-03-16 | 2026-03-16 | 100% | P0-04 | Doc review | Merged to dev, branch deleted
Phase 1
Phase 1 | 7 | P1-01 | Backend | API scaffold | FastAPI app boots, settings, health endpoints, dependency checks, tests pass | feature/phase1-api-scaffold | Completed | High | Anoushka | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | P0-06 | 3 unit tests + manual endpoint verification | Root, docs, /health, /health/dependencies verified
Phase 1 | 8 | P1-02 | Infra | Docker infra | docker-compose for Postgres, Qdrant, Redis; startup verified | feature/phase1-infra-docker | Completed | High | Anoushka | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | P1-01 | Service startup smoke tests | Merged to dev, branch deleted
Phase 1 | 9 | P1-03 | Backend | DB schema + models | Initial relational schema for reservations, orders, complaints, traces | feature/phase1-db-schema | Completed | High | Anoushka | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | P1-02 | Schema tests / migrations sanity | Merged to dev, branch deleted
Phase 1 | 10 | P1-04 | Data | Seed data | Pizza-heavy synthetic data with Friday spikes and simulated reservation/review sources | feature/phase1-seed-data | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-03 | Seed script smoke tests | Merged to dev, branch deleted
Phase 1 | 11 | P1-05 | Backend | LLM provider layer | Base provider + Gemini provider , Groq Provider + prompt utilities | feature/phase1-llm-provider | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-01 | Provider unit/integration tests | Merged to dev, branch deleted
Phase 1 | 12 | P1-06 | Backend | Core services | Reservation analytics, baseline forecast, complaint summary, critic rules | feature/phase1-core-services | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-03 | Unit tests for services/rules | Merged to dev, branch deleted
Phase 1 | 13 | P1-07 | Memory | Qdrant memory | Collections, embeddings, retrieval helpers for complaints/SOPs | feature/phase1-qdrant-memory | Completed | Medium | Anoushka | 2026-04-05 | 2026-04-05 | 2026-04-05 | 100% | P1-02, P1-05 | Integration tests with retrieval | Merged to dev, branch deleted
Phase 1 | 14 | P1-08 | Agents | LangGraph skeleton | Shared state, nodes, graph edges, stub flow | feature/phase1-langgraph-skeleton | Completed | High | Anoushka | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | P1-05, P1-06 | Graph flow tests | Merged to dev, branch deleted
Phase 1 | 15 | P1-09 | Backend | Friday rush endpoint | End-to-end planning endpoint + aggregated recommendation + trace write | feature/phase1-friday-rush-endpoint | Completed | High | Anoushka | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | P1-06, P1-07, P1-08 | Integration + manual demo test | Merged to dev, branch deleted
Phase 1 | 16 | P1-10 | Frontend | Dashboard MVP | Planning result UI with forecast, complaint, critic, trace sections | feature/phase1-dashboard | Completed | Medium | Anoushka | 2026-04-10 | 2026-04-11 | 2026-04-11 | 100% | P1-09 | Frontend smoke tests | Merged to dev, branch deleted
Phase 1 | 17 | P1-11 | Quality | Phase 1 tests | Unit + integration + first E2E Friday rush flow | feature/phase1-tests | Completed | High | Anoushka | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | P1-09, P1-10 | Pytest + scenario checklist | Merged to dev, branch deleted
Phase 1 | 18 | P1-12 | Release | Sync Phase 1 to main | Stable MVP milestone on main | dev -> main PR | Completed | High | Anoushka | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | P1-11 | Milestone verification | Main synced
Phase 2
Phase 2 | 19 | P2-01 | Forecasting | Prophet upgrade | Replace/add baseline with Prophet forecasting path | feature/phase2-prophet-upgrade | Completed | Medium | Anoushka | 2026-04-16 | 2026-04-17 | 2026-04-19 | 100% | P1-12 | Forecast comparison tests | Merged to dev, branch deleted
Phase 2 | 20 | P2-02 | Ops | Inventory alerts | Shortage/overstock alerts using forecast + stock levels | feature/phase2-inventory-alerts | Completed | Medium | Anoushka | 2026-04-19 | 2026-04-19 | 2026-04-20 | 100% | P2-01 | Rule tests | Merged to dev, branch deleted
Phase 2 | 21 | P2-03 | Menu | Menu insights | Top/weak items and promo suggestions surfaced in API/UI | feature/phase2-menu-insights | Completed | Medium | Anoushka | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | P1-12 | Menu service, node, graph, and e2e tests passed | Merged to dev, branch deleted
Phase 2 | 22 | P2-04 | Frontend | Dashboard enhancement | Product-grade dashboard with stronger layout hierarchy, dedicated agent panels, top summary KPIs, clearer operational sections, and drill-down-ready UI | feature/phase2-dashboard-enhancement | Completed | High | Anoushka | 2026-04-21 | 2026-04-22 | 2026-04-26 | 100% | P2-02, P2-03 | Frontend checks + UI walkthrough + dashboard smoke tests | Merged to dev, branch deleted , (force-with-lease)
Phase 2 | 23 | P2-05 | Quality | Evaluation refinement | Manual rubric + scenario checklist + automated sanity checks (schema validation, quantity realism, 24h feasibility) + critic calibration notes | feature/phase2-evaluation-refinement | Completed | High | Anoushka | 2026-04-26 | 2026-04-26 | 2026-04-26 | 100% | P2-01, P2-02, P2-03, P2-04 | Eval checks + scenario validation + rubric doc | Merged to dev, branch deleted
Phase 2 | 24 | P2-06 | Release | Sync Phase 2 to main | Phase 2 milestone verified on main (forecast + inventory + menu + dashboard + evaluation); release verification + notes | dev -> main PR | Completed | Medium | Anoushka | 2026-04-26 | 2026-04-26 | 2026-04-26 | 100% | P2-05 | Milestone verification checklist | Main synced
Phase 3
Phase 3 | 25 | P3-01 | Product | Runs & audit UI | Run history persisted in Postgres; runs list + drilldown page showing agent outputs, critic score, rag context, trace/audit ids | feature/phase3-runs-audit-ui | Completed | Medium | Anoushka | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | P2-06 | API contract tests + UI smoke tests + trace retrieval tests | Merged to dev, branch deleted
Phase 3 | 26 | P3-02 | Quality | Advanced critic | Richer scoring dimensions + clearer revision reasons + actionable critic feedback for weak recommendations | feature/phase3-advanced-critic | Completed | Medium | Anoushka | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | P3-01 | Critic tests + scenario review + regression checks | Merged to dev, branch deleted
Phase 3 | 27 | P3-03 | Scoring | Cost-aware scoring | Recommendation scoring with operational cost/benefit awareness (prep burden, stock risk, feasibility tradeoffs) | feature/phase3-cost-aware-scoring | Completed | Medium | Anoushka | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | P3-02 | Rule tests + scoring checks + e2e scenario tests | Merged to dev, branch deleted
Phase 3 | 28 | P3-04 | Product | Scenario expansion | Extend beyond Friday Rush (weekday/weekend, holiday spike, low-stock weekend); reusable workflow framing + UI selection | feature/phase3-scenario-expansion | Completed | Medium | Anoushka | 2026-04-28 | 2026-04-29 | 2026-04-29 | 100% | P3-03 | Scenario tests + e2e flow tests + UI smoke tests | Merged to dev, branch deleted
Phase 3 | 29 | P3-05 | Release | Sync Phase 3 to main | Advanced milestone stabilized on main | dev -> main PR | Completed | Low | Anoushka | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | P3-04 | Milestone verification checklist + demo run checklist | Main synced
Demo prep
Demo prep | 30 | PD-01 | Data | Seed data | Additional Seed Data for demo and minor ui polish | chore/seed-data | Completed | Low | Anoushka | 2026-05-16 | 2026-05-16 | 2026-05-16 | 100% | NONE | Seeded Data successfully | Merged to dev, branch deleted
Demo prep | 31 | PD-02 | Frontend | minor ui polish | minor ui polish | feat/demo-prep | Completed | Low | Anoushka | 2026-05-16 | 2026-05-16 | 2026-05-16 | 100% | NONE | Ui polish pass | Merged to dev, branch deleted
Demo prep | 31 | PD-03 | Frontend | loading state improvements | minor ui polish | feat/quick-fix | Completed | Low | Anoushka | 2026-05-19 | 2026-05-19 | 2026-05-19 | 100% | NONE | Ui polish pass | Merged to dev, branch deleted
Phase 4
Phase 4 | 1 | P4-01 | Product | Multi-tenant + auth | Users/orgs, login, workspace separation, role-based access, protected pages | feature/phase4-auth-multitenant | Completed | High | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P3-05 | Auth tests + access-control tests + UI smoke tests | Merged to dev, branch deleted
Phase 4 | 2 | P4-02 | Observability | LangSmith tracing | Enable LangSmith trace capture for all LangGraph nodes — set LANGCHAIN_TRACING_V2 + API key; verify per-node traces visible in LangSmith UI | feature/phase4-langsmith-tracing | Completed | High | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P3-05 | Trace visibility smoke test — confirm node names, LLM calls, latency appear in LangSmith dashboard | Merged to dev, branch deleted
Phase 4 | 3 | P4-03 | Infra | Real dependency health checks | Replace stub URL-existence checks in dependency_health.py with actual pings: psycopg2.connect(), QdrantClient.get_collections(), redis.ping(); return latency_ms and error detail per dependency | feature/phase4-health-checks | Completed | High | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P3-05 | Health check integration tests — confirm each service returns ok=True when running, ok=False when stopped | Merged to dev, branch deleted
Phase 4 | 4 | P4-04 | Observability | Structured logging (structlog) | Replace default FastAPI logging with structlog JSON output: run_id, node, duration_ms on every event; add request middleware for HTTP access logs | feature/phase4-structlog | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-02 | Log output unit tests — verify JSON fields present; smoke test that run_id propagates through nodes | Merged to dev, branch deleted
Phase 4 | 5 | P4-05 | Observability | Node latency + LLM cost tracking | Record started_at/ended_at/duration_ms per node in execution_trace (always-on, not debug-only); add prompt_tokens, completion_tokens, cost_usd per LLM call using Gemini usage API; store in planning_runs.meta (jsonb) | feature/phase4-cost-latency | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-04 | Cost tracking unit tests — verify token fields populated; integration test checks meta column written after run | Merged to dev, branch deleted
Phase 4 | 6 | P4-06 | Product | Admin + settings | Scenario templates, thresholds, capacity, menu/inventory settings, tenant config UI | feature/phase4-admin-settings | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-01 | UI smoke tests + settings persistence tests | Merged to dev, branch deleted
Phase 4 | 7 | P4-07 | Product | Runs UI — filter + diff view | Add scenario filter, date range picker, and critic score trend chart to /runs page; add side-by-side diff modal comparing critic dimension scores between two selected runs | feature/phase4-runs-diff-ui | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-01 | Frontend smoke tests + API filter parameter tests | Merged to dev, branch deleted
Phase 4 | 8 | P4-08 | Product | Configurable restaurant profiles | Add restaurant_profiles table (name, cuisine, capacity, peak_hours, timezone); planning run accepts restaurant_id; scenarios pull context from profile instead of hardcoded pizza assumptions; one Alembic migration | feature/phase4-restaurant-profiles | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-06 | Migration smoke test + service unit tests + scenario context injection tests | Merged to dev, branch deleted
Phase 4 | 9 | P4-09 | Infra | LLM provider hot-swap + fallback | LLM_PROVIDER env var selects active provider (gemini¦groq); if primary fails mid-run, automatically retry with fallback provider; log provider used per run in structlog and LangSmith metadata | feature/phase4-llm-providers | Completed | Low | Anoushka | 2026-06-01 | 2026-06-01 | 2026-06-01 | 100% | P4-02 | Provider unit tests — verify complete() and complete_json() work for new providers; integration test with one full planning run per provider | Merged to dev, branch deleted
Phase 4 | 10 | P4-10 | Quality | RAGAS eval for complaint RAG pipeline | Integrate ragas to evaluate complaint_intelligence node: faithfulness, answer relevancy, context precision/recall scored against Qdrant retrieval; run as part of eval suite with LangSmith dataset | feature/phase4-ragas-evals | Completed | Low | Anoushka | 2026-06-01 | 2026-06-01 | 2026-06-01 | 100% | P4-02 | RAGAS metric thresholds pass (faithfulness > 0.8); eval script runs without error in CI | Merged to dev, branch deleted
Phase 4 | 11 | P4-11 | Quality | DeepEval LLM output quality tests | Add deepeval metrics to pytest suite: HallucinationMetric on critic output, AnswerRelevancyMetric on agent recommendations; gate CI — fail if quality drops below threshold | feature/phase4-deepeval | Completed | Low | Anoushka | 2026-06-03 | 2026-06-03 | 2026-06-03 | 100% | P4-10 | DeepEval tests pass in pytest; CI pipeline fails on hallucination score above threshold | Merged to dev, branch deleted
Phase 4 | 12 | P4-12 | Infra | MCP server — expose planning API | Wrap POST /planning/run and GET /runs as MCP tools using Anthropic Python MCP SDK; expose run_planning_scenario tool and get_run_history resource; test with Claude Desktop | feature/phase4-mcp-server | Completed | Low | Anoushka | 2026-06-03 | 2026-06-03 | 2026-06-03 | 100% | P4-01 | MCP tool smoke test — confirm Claude Desktop can trigger a planning run and retrieve run history | Merged to dev, branch deleted
Phase 4 | 13 | P4-13 | Release | Sync Phase 4 to main | Phase 4 milestone verified on main: auth, observability, evals, Redis cache, MCP server all stable. README updated. Demo run clean across all 4 scenarios. | dev -> main PR | Completed | Low | Anoushka | 2026-06-03 | 2026-06-03 | 2026-06-03 | 100% | P4-12 | Milestone verification checklist + demo run checklist + all Phase 4 integration tests green | Merged to main via dev PR
Phase 5
Phase 5 | 1 | P5-01 | Product | PDF export — manager summary | GET /runs/{id}/export?format=pdf — one-page summary with critic score, action items, forecast; WeasyPrint or reportlab; downloadable from runs page | feature/phase5-pdf-export | Completed | High | Anoushka |  |  |  | 0% | P4-13 | PDF generation unit test — all sections present; download endpoint smoke test | No blockers — quick win, strong demo artifact
Phase 5 | 2 | P5-02 | Product | Excel export — role-aware | GET /runs/{id}/export?format=xlsx — inventory + staffing sheet for chef, cost breakdown for owner; formatted with openpyxl; separate sheets per role | feature/phase5-excel-export | Completed | High | Anoushka |  |  |  | 0% | P5-01 | Excel generation unit test — verify sheets and headers; download endpoint smoke test | Pairs with P5-01
Phase 5 | 3 | P5-03 | Product | Frontend UX fixes | Fix /data-health 404 (page missing, NavBar links to it); add restaurant profile selector to dashboard run form; add export download buttons to runs page; add input validation to settings page; surface cost/token aggregate on runs list | feature/phase5-frontend-ux | Completed | High | Anoushka |  |  |  | 0% | P5-01 | Smoke tests: data-health loads; profile selector sends restaurant_id; settings rejects invalid range | Fixes live 404 bug. Frontend-only — no API changes needed
Phase 5 | 4 | P5-04 | Infra | Redis caching for planning runs | Cache planning run results by scenario+date key (TTL 1hr) using aioredis; skip full graph on cache hit; add cache_hit flag to response; Redis already in docker-compose | feature/phase5-redis-cache | Completed | Medium | Anoushka |  |  |  | 0% | P4-13 | Cache unit tests — hit/miss logic; integration test: second identical run returns faster with cache_hit=True | Redis already running — no infra change needed
Phase 5 | 5 | P5-05 | Infra | SSE streaming — node-by-node results | Stream planning run results node-by-node to frontend via Server-Sent Events; frontend renders each agent card as its node completes; reduces perceived latency significantly | feature/phase5-streaming | Completed | Medium | Anoushka |  |  |  | 0% | P5-04 | SSE endpoint smoke test — events emitted per node; frontend confirms cards render progressively | No async queue needed — SSE works on sync runs
Phase 5 | 6 | P5-06 | Product | What-if simulator | Sliders for covers/date/scenario in UI — re-run only forecast + cost nodes via partial LangGraph execution — instant updated output without full planning run | feature/phase5-whatif-simulator | Completed | Medium | Anoushka |  |  |  | 0% | P4-08 | Partial graph execution unit test; UI slider integration test; output diff from full run test | No blockers — works with synthetic data, strong interactive demo
Phase 5 | 7 | P5-07 | Observability | OpenTelemetry + Prometheus metrics | Add opentelemetry-instrumentation-fastapi + prometheus-fastapi-instrumentator; expose /metrics endpoint; capture HTTP request latency, throughput, error rate; Grafana dashboard | feature/phase5-opentelemetry | Completed | Medium | Anoushka |  |  |  | 0% | P4-05 | Prometheus scrape test — /metrics returns valid prom format; Grafana panels show data | Pure infra — no data dependency
Phase 5 | 8 | P5-08 | Infra | Sentry error tracking | Add sentry-sdk[fastapi]; capture unhandled exceptions, slow transactions, LangGraph node errors; verify error appears in Sentry on intentional 500 | feature/phase5-sentry | Completed | Low | Anoushka |  |  |  | 0% | P4-05 | Sentry capture smoke test — intentional exception appears within 30s | Quick win — ~1 day effort
Phase 5 | 9 | P5-09 | Quality | LangSmith dataset + regression evals | Build golden dataset from best historical planning runs already in DB; run automated evaluators (critic score > 3.5, plan contains restock recommendation); fail CI on regression | feature/phase5-langsmith-evals | Completed | Medium | Anoushka |  |  |  | 0% | P4-02 | Eval pass rate > 90% on golden dataset; CI fails on intentional prompt regression | We already have runs in the DB — use those as golden dataset
Phase 5 | 10 | P5-10 | Product | Multi-tenant workspace isolation | Full tenant isolation: Postgres row-level security per org; Qdrant shared collection with restaurant_id + doc_type payload filters (NOT per-tenant collections — see D-009); no data bleed between orgs | feature/phase5-tenant-isolation | Completed | High | Anoushka |  |  |  | 0% | P4-01 | Tenant isolation tests — verify org A cannot read org B runs; Qdrant filter tests | Auth done in P4-01. Qdrant: payload pre-filter only, not per-tenant collections
Phase 5 | 11 | P5-11 | Product | Weekly digest email | Auto-generated Sunday summary + Monday recommendations via APScheduler; formatted email via SendGrid/Resend; per-restaurant scheduling; PDF attached | feature/phase5-weekly-digest | Completed | Medium | Anoushka |  |  |  | 0% | P5-01 | Scheduler unit test; email template render test; send smoke test with test API key | Works with synthetic data — auth and PDF export must be done first
Phase 5 | 12 | P5-12 | Product | RAG chatbot over run history | Conversational interface: answer questions like why did critic score drop last Friday — retrieves relevant runs + complaints from Postgres + Qdrant, streams reply via SSE; multi-turn memory | feature/phase5-rag-chatbot | Completed | High | Anoushka |  |  |  | 0% | P5-05 | Retrieval unit test; multi-turn memory test; SSE streaming smoke test; hallucination check via DeepEval | SSE must be done first (P5-05). Works with synthetic run history
Phase 5 | 13 | P5-13 | Release | Sync Phase 5 to main | Phase 5 milestone verified: PDF/Excel export, SSE streaming, Redis cache, tenant isolation all stable. README and docs updated. | dev -> main PR | Completed | Low | Anoushka |  |  |  | 0% | P5-12 | Milestone checklist + demo run with all Phase 5 features active | Update docs after merge
Phase 6
Phase 6 | 0 | P6-00 | Infra | Per-node model tier routing via CometAPI | CometProvider (AsyncOpenAI), 3-tier registry (fast/balanced/strong), llm_registry in OrchestratorState, node-level tier overrides, cost tracking across all tiers. LangSmith verified per-node model assignment. Async fix cut fan-out from 48.7s to 17s. | feature/per-node-model-routing | Completed | High | anoushka | 2026-06-19 | 2026-06-19 | 2026-06-19 | 100% |  | No | Merged to dev 2026-06-19. PR: feat: per-node model tier routing via CometAPI
Phase 6 | 0 | P6-00b | Agents | Cross-agent assumption diffing | Each domain node writes assumptions dict to OrchestratorState after its service call. EvaluationSanityChecker._diff_assumptions() cross-diffs them post fan-out (4 checks: stockout, capacity, forecast confidence, complaint gray zone). stale_assumptions injected into critic LLM prompt and returned in critic.stale_assumptions in API response. final_assembler bug fix included. 9 docs updated. | feature/assumption-diffing | Completed | High | Anoushka | 2026-06-26 | 2026-06-26 | 2026-06-26 | 100% | P6-00 | Unit tests: existing EvaluationSanityChecker tests still pass; stale_assumptions in check_bundle output | Merged to dev, branch deleted
Phase 6 | 0 | P6-00c | Agents | Drop Diff 1, v3 reseed, stale_assumptions fix | Dropped false-positive Diff 1. v3 seed data. stale_assumptions passthrough fixed. | feature/drop-diff1-reseed-data | Completed | High | Anoushka | 2026-06-26 | 2026-06-26 | 2026-06-26 | 100% | P6-00b | Existing diffs pass; API returns stale_assumptions | Merged to dev
Phase 6 | 1 | P6-S01 | Integrations | BaseConnector + SwiggyMCPClient | BaseConnector ABC (sync/enrich), SwiggyMCPClient (JSON-RPC 2.0, httpx, graceful degradation — never raises), SwiggyConnector skeleton, enrichers/ + executor/ package stubs, CLAUDE.md at root, swiggy_access_token + swiggy_address_id in settings | feature/swiggy-base-connector | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-27 | 2026-06-27 | 1 | P6-00c | 7 tests: is_available True/False; call_tool returns None on 401, 500 (x2 retry verified), success data dict, never raises on Exception, returns None on success=false | Merged to dev 2026-06-27. PR #80. CLAUDE.md created. Migration verified live on DB.
Phase 6 | 2 | P6-S02 | Infra | connectors table + async job queue | Alembic migration b3e1f2a9c5d7: connectors table (11 cols, uq org+type), orders.source/channel/external_order_id, reservations.source/external_booking_id, feedback delivery timing cols, swiggy_delivery enum value. ConnectorRepository (upsert, token, sync status). Redis async job queue (24h TTL, uuid4 IDs, no external library). | feature/swiggy-base-connector | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-27 | 2026-06-27 | 1 | P6-S01 | 6 tests: upsert creates, upsert idempotent (1 row), get returns None, error_count increments, error clears on success, list_active filter. Migration smoke: alembic upgrade head + psycopg2 verify all cols + enum. | Merged to dev 2026-06-27. PR #80. Migration verified live on Docker Postgres.
Phase 6 | 3 | P6-S03 | Integrations | SwiggyOrderSyncService — get_food_orders → orders table | SwiggyOrderSyncService.sync(address_id): fetches up to 20 Swiggy delivery orders, creates one Order row per item (source=swiggy, channel=delivery, is_delivery=True, external_order_id={orderId}_{idx}). _get_or_create_menu_item: case-insensitive name match; placeholder (is_available=False) if no match. Idempotent. SwiggyConnector.sync() implemented: reads SWIGGY_ADDRESS_ID, sets connector status syncing→success/error. BaseConnector updated: db: Session added to __init__. | feature/swiggy-sync-orders | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-27 | 2026-06-27 | 1 | P6-S02 | 8/8 pass: correct count, Order fields, placeholder MenuItem, reuse existing MenuItem, idempotency, None graceful, empty list, ext_id format | Merged to dev 2026-06-27. Mock-first (no Swiggy token needed). Live integration test pending token.
Phase 6 | 4 | P6-S04 | Agents + Infra | Agent Intelligence Bundle | Aggregator contradiction detection (0 LLM calls). Critic replanning loop max 2 retries. Qdrant early enrichment layer. Semantic cache (planning + chatbot, Qdrant, threshold 0.92). Chatbot tool use via Groq function calling. Cross-session memory in Qdrant. Proactive pattern surfacing on session start. | feature/agent-intelligence | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-28 |  | 100 | P6-S03 | Contradiction fires; replanning routes correctly; cache hit; chatbot tools return data; cross-session memory persists | Building now (2026-06-27). Mock-first where needed. No Swiggy token required.

## Phase 6
Task ID | Feature Branch | Workstream | Task | Detailed Outcome / Done Means | PR Description Hook | Docs Updated | Status | Priority | Owner | Start | Target | % Done | Depends On | Tests Expected
P6-00 | feature/per-node-model-routing | Infra | Per-node model tier routing via CometAPI | CometProvider (AsyncOpenAI), 3-tier registry (fast/balanced/strong), llm_registry in OrchestratorState, node-level tier overrides, cost tracking. Fan-out latency: 48.7s → 17s. | feat: per-node model tier routing via CometAPI | docs/ARCHITECTURE.md, docs/DECISIONS.md | Completed | High | Anoushka | 2026-06-19 | 2026-06-19 | 100% | P5-13 | LangSmith traces show per-node model; cost_usd tracked per tier
P6-00b | feature/assumption-diffing | Agents | Cross-agent assumption diffing | 4 domain nodes write assumptions dicts. EvaluationSanityChecker._diff_assumptions() runs 3 cross-diffs post fan-out. stale_assumptions injected into critic prompt + returned in API. final_assembler bug fix. 9 docs updated. | feat: cross-agent assumption diffing — O(N²) → O(N) | 9 docs updated | Completed | High | Anoushka | 2026-06-26 | 2026-06-26 | 100% | P6-00 | Existing sanity checker tests pass; stale_assumptions in API response
P6-00c | feature/drop-diff1-reseed-data | Agents | Drop Diff 1, v3 reseed, stale_assumptions API fix | Diff 1 removed (MenuService self-queries inventory — parallel execution means diff fires as false positive). v3 seed data. stale_assumptions passthrough fixed in final_assembler. | fix: drop Diff 1 false positive, v3 reseed, stale_assumptions API fix | docs/AGENTS.md | Completed | High | Anoushka | 2026-06-26 | 2026-06-26 | 100% | P6-00b | 3 remaining diffs fire correctly; API response carries stale_assumptions
P6-S01 | feature/swiggy-base-connector | Integrations | BaseConnector + SwiggyMCPClient | Abstract BaseConnector ABC with sync() and enrich() methods. SwiggyMCPClient: per-org OAuth token (5-day TTL, re-auth on 401, encrypted storage), JSON-RPC 2.0 calls to /food + /im + /dineout, exponential backoff retry, is_available() check, structured logging. Absorbs original P6-01. | feat: connector layer — BaseConnector ABC + SwiggyMCPClient with per-org OAuth | docs/ARCHITECTURE.md (connector layer section), docs/DECISIONS.md (D-019), docs/DATA_MODEL.md, CLAUDE.md (new), docs/SWIGGY_INTEGRATION.md | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-27 | 100% | P6-00c | 13/13 pass — test_swiggy_client.py (7): is_available, 401 no-retry, 500 retry x2, success data, never raises, success=false; test_connector_repository.py (6): upsert create, upsert idempotent, get none, error_count increment, error clear on success, list_active filter
P6-S02 |  | Infra | connectors table + async job queue | Alembic migration: connectors table (org_id, connector_type, access_token_encrypted, token_expires_at, last_sync_at, sync_status, error_count). Redis job queue for async planning runs (absorbs original P6-02): job_id, status endpoint, dedup by scenario+date, non-blocking HTTP. | feat: connectors table + async Redis job queue for planning runs | docs/DATA_MODEL.md (connectors table, orders/reservations/feedback new cols), docs/ARCHITECTURE.md, docs/DECISIONS.md (D-019) | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-27 | 100% | P6-S01 | Migration smoke test (alembic upgrade head verified live on DB); connectors table + all new cols confirmed via psycopg2; swiggy_delivery enum value present
P6-S03 | feature/swiggy-sync-orders | Integrations | Sync Swiggy orders → orders table | Completed — NOTE: syncs PERSONAL consumer orders (your Swiggy food deliveries), NOT a restaurant incoming orders. Swiggy MCP is consumer-facing. Restaurant order data needs Swiggy Partner API. Sync infrastructure built but data is not meaningful for restaurant planning nodes. | feat: swiggy order sync — get_food_orders nightly → orders table (source=swiggy, channel=delivery) | docs/SWIGGY_INTEGRATION.md (P6-S03 ✅, status header updated) | Completed | High | Anoushka | 2026-06-27 | 2026-06-27 | 100% | P6-S02 | 8/8 pass — correct count, correct Order fields (source/channel/is_delivery), placeholder MenuItem creation (is_available=False, category=swiggy_import), reuse existing MenuItem by name, idempotency on duplicate sync, None call_tool graceful, empty order list, external_order_id format SW-001_0/SW-001_1
P6-S03b | feature/swiggy-base-connector | Infra | Redis-backed circuit breaker for SwiggyMCPClient | 3 failures in 5 min → circuit opens for 30 min, auto-resets via TTL. On Redis down → fail open (let call through). Per-endpoint circuit keys. Added beyond spec — production resilience for Swiggy MCP calls. Integrated into call_tool() in SwiggyMCPClient. | feat: Redis circuit breaker for Swiggy MCP calls — 3-failure threshold, 30min open, fail-open on Redis down | docs/ARCHITECTURE.md (circuit breaker section), docs/SWIGGY_INTEGRATION.md | Completed | High | Anoushka |  | W2 | 100% | P6-S01 | Circuit opens after 3 failures; auto-resets after 30min; fail-open when Redis unavailable; call_tool() returns None immediately when circuit open
P6-S03c |  | Infra | Capability-to-provider registry | Maps planning capabilities to ordered provider lists: competitor_pricing → [swiggy, zomato], reservation_data → [swiggy, eazydiner], procurement → [swiggy], order_history → [swiggy, zomato]. Routes to highest-priority provider with active connector row for the org. Adding Zomato = 1 new connector file + 1 registry entry. No DB migration needed — reads from connectors table. | feat: ProviderRegistry — capability routing with multi-provider fallback, future Zomato/EazyDiner-ready | docs/ARCHITECTURE.md (provider registry section), docs/CONNECTORS.md | Completed | High | Anoushka |  | W2 | 100% | P6-S02 | competitor_pricing routes to swiggy when active; routes to zomato when swiggy connector missing; list_active used to determine available providers
P6-S04 | feature/agent-intelligence | Agents + Infra | Agent Intelligence Bundle — smarter pipeline + agentic chatbot | Aggregator contradiction detection (pure Python, 0 LLM calls): detects demand_forecast vs inventory conflicts, appends DETECTED CONTRADICTIONS to critic summary. Critic replanning loop: rejected/revision → replan_orchestrator injects critic notes → aggregator re-runs → critic re-evaluates, max 2 retries (+1 LLM call/retry). Qdrant early enrichment: 1 shared retrieval step before parallel nodes, all agents get pre-loaded context. Semantic cache: Qdrant embedding-based lookup (threshold 0.92) for planning runs + chatbot queries. Chatbot tool use: Groq function calling — query_runs, get_run_detail, trigger_planning_run, get_inventory_status. Cross-session memory: Qdrant session summaries per user. Proactive pattern surfacing: chatbot detects recurring critic failures on session start. | feat: agent intelligence — contradiction detection, replanning loop, semantic cache, agentic chatbot | docs/ARCHITECTURE.md (replanning loop, Qdrant enrichment), docs/AGENTS.md (aggregator update) | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-28 | 100% | P6-S03 | Contradiction detection: demand_forecast vs inventory conflict fires correctly. Replanning: rejected plan routes back, critic re-evaluates with notes. Semantic cache: cache hit returns plan without LLM call. Chatbot tools: query_runs returns structured data; trigger_planning_run starts a run. Cross-session memory: session summary persists in Qdrant, retrieved on next session.
P6-S05 | feature/swiggy-sync-feedback-reservations | Integrations | Reservation sync skeleton → reservations table | Completed — NOTE: syncs PERSONAL Dineout reservations (tables you booked at other restaurants), NOT your restaurant table bookings. Infrastructure built; data not useful for reservation planning node. | feat: reservation sync skeleton — get_booking_status → reservations table, register_booking_order_id for DineoutExecutor (P6-S31) | CLAUDE.md, docs/SWIGGY_INTEGRATION.md (schemas), docs/APIS.md (connectors endpoints) | Completed | High | Anoushka | 2026-06-29 | 2026-06-29 | 100% | P6-S04 | test_swiggy_reservation_sync.py (5 tests)
P6-S06 |  | Integrations | Sync delivery performance → feedback table | Completed — NOTE: syncs YOUR personal delivery tracking data as a consumer, NOT restaurant delivery performance. Infrastructure built; complaint_intelligence uses internal feedback data instead. | feat(P6-S05/S06): fix Swiggy client response format + live sync endpoint + feedback sync + reservation sync skeleton | CLAUDE.md, docs/SWIGGY_INTEGRATION.md (section 3 auth + all section 16 schemas fixed to real format), docs/APIS.md | Completed | High | Anoushka | 2026-06-29 | 2026-06-29 | 100% | P6-S03 | test_swiggy_feedback_sync.py (7 tests), test_swiggy_client.py updated (406 + Accept header + new format)
P6-S07 | feature/swiggy-market-intel-enrichers | Agents | CompetitorEnricher — Food MCP | Create enrichers/competitor.py. get_addresses → addressId. search_restaurants (cuisine, addressId) → filter OPEN → search_menu + get_restaurant_menu per restaurant (max 3). Build competitor_pricing dict: area avg price per dish category, pricing_alerts vs your menu. Redis cache 30min TTL. Inject into menu_intel node prompt as ## Market Context section. | feat: CompetitorEnricher — live competitor pricing via Food MCP | get_addresses, search_restaurants, search_menu, get_restaurant_menu | Completed | High | Anoushka | 2026-06-30 | 2026-06-30 | 100% | P6-S05 | NEEDS: OAuth token. All read-only — works on production endpoint.
P6-S08 |  | Agents | OccupancyEnricher — Dineout MCP | Create enrichers/occupancy.py. get_saved_locations → store lat/lng. search_restaurants_dineout (cuisine, addressId) → get_restaurant_details (top 3) → get_available_slots (today). Compute occupancy_signal: HIGH if >50% slots have availabilityCount < 2. Redis cache 30min TTL. Inject into reservation node prompt. | feat: OccupancyEnricher — live competitor occupancy via Dineout MCP | get_saved_locations, search_restaurants_dineout, get_restaurant_details, get_available_slots | Completed | High | Anoushka |  | 2026-06-30 | 100% | P6-S07 | NEEDS: OAuth token. All read-only.
P6-S09 |  | Agents | ProcurementEnricher — Instamart MCP | Create enrichers/procurement.py. search_products (per shortage item, max 5 calls/run) + your_go_to_items (frequent reorders). Output: [{ingredient, spinId, price, unit, inStock}]. spinId MUST persist in OrchestratorState — required for Instamart checkout in P6-S30. Redis cache 30 min. Returns None on any failure; inventory node falls back to its own analysis. | feat: ProcurementEnricher — live Instamart prices + spinIds injected into inventory node | docs/SWIGGY_INTEGRATION.md (P6-S09 section) | Completed | High | Anoushka |  | 2026-06-30 | 100% | P6-S08 | NEEDS: OAuth token (read-only). Returns None on client failure; correct procurement_options on success; spinId present in each item; Redis caches result; max 5 search_products calls per run enforced.
P6-S10 | feature/swiggy-market-intel-node | Infra | MarketIntelService + 6 new OrchestratorState fields | MarketIntelService orchestrates all 3 enrichers. Adds 6 Annotated[Optional[Dict], keep_last] fields to OrchestratorState: swiggy_competitor_context, swiggy_occupancy_context, swiggy_procurement_options, swiggy_delivery_signal, market_intel_output, dineout_manager_output. | feat: MarketIntelService + 6 new OrchestratorState enrichment fields | docs/ARCHITECTURE.md (MarketIntelService), docs/DATA_MODEL.md (state fields) | Completed | High | Anoushka | 2026-07-01 | 2026-07-01 | 100% | P6-S07, P6-S08, P6-S09 | State field type tests; MarketIntelService runs all 3 enrichers; final_assembler passes through
P6-S11 |  | Agents | market_intel_node — 10th LangGraph node | New parallel domain node. Runs CompetitorEnricher + OccupancyEnricher. Outputs market_intel_output: competitor_pricing, area_occupancy, pricing_alerts. Writes market_assumptions dict. Participates in assumption diffing. Critic receives market context. Supersedes original P6-06. | feat: market_intel_node — 10th parallel LangGraph node, Swiggy-powered market awareness | docs/AGENTS.md (market_intel_node section), docs/ARCHITECTURE.md (11-node pipeline), docs/DECISIONS.md (D-020) | Completed | High | Anoushka | 2026-07-01 | 2026-07-01 | 100% | P6-S10 | Node writes market_intel_output + market_assumptions; parallel verified; assumption diffing fires; LangSmith trace shows node
P6-S12 |  | Agents | dineout_manager_node — 11th LangGraph node | Built. Node wired into LangGraph fan-out and exits gracefully when SWIGGY_DINEOUT_RESTAURANT_ID not set. NOTE: Consumer MCP cannot manage your own restaurant Dineout slots — book_table is a consumer action (books at other restaurants). Dineout slot management needs Swiggy Partner API. Current value: competitive occupancy signal only (get_available_slots on competitors). | feat: dineout_manager_node — own Dineout slot monitoring wired into planning pipeline | docs/AGENTS.md (dineout_manager_node spec) | Completed | Medium | Anoushka | 2026-07-01 | 2026-07-01 | 100% | P6-S10 | Node runs in parallel fan-out; dineout_assumptions written to state; action queued when slots low + walk-in predicted high; graceful None on Swiggy failure.
P6-S13 |  | Agents | Assumption diffs 5 + 6 for new nodes | Diff 5: market_intel assumed_competitor_avg_price vs menu_intel items_assumed_available pricing. Diff 6: dineout_manager assumed_dineout_slots_low vs reservation assumed_peak_occupancy. Extends P6-00b. Total now 5 active diffs. | feat: assumption diffs 5+6 — market vs menu pricing, dineout slots vs reservation occupancy | docs/ARCHITECTURE.md (sanity checker updated), docs/AGENTS.md | Completed | Medium | Anoushka | 2026-07-01 | 2026-07-01 | 100% | P6-S11, P6-S12 | Diff 5 + 6 fire correctly; existing 3 diffs unaffected; stale_assumptions includes new conflicts
P6-S13c | feature/swiggy-chatbot-tools | Product | Swiggy-aware chatbot tools — HIGH PRIORITY FOR DEMO | Add 3 Groq function-calling tools to the existing agentic chatbot (P6-S04). search_menu(query, addressId): answers questions like 'what is the avg biryani price near me?' get_food_orders(addressId): answers 'what were my top Swiggy items last week?' search_products(query, addressId): answers 'what does cream cost on Instamart right now?' Makes the chatbot genuinely Swiggy-aware — very demo-friendly for the Swiggy team. | feat: Swiggy chatbot tools — search_menu, get_food_orders, search_products via Groq function calling | docs/AGENTS.md (chatbot Swiggy tools section) | Completed | High | Anoushka | 2026-07-01 | 2026-07-01 | 100% | P6-S04, P6-S01 | NEEDS: OAuth token (read-only). All 3 tools callable from /chat; correct Swiggy data returned; graceful None on Swiggy failure; tool names appear in Groq tool_calls response.
P6-F14 | feature/swiggy-connectors-ui | Frontend | /connectors page — data source management | New route /connectors. Lists connectors with status badges (Connected/Disconnected/Error). Shows last sync time, records synced, data freshness. Connect button triggers OAuth flow. Disconnect revokes token. Error state shows last error + reconnect. Works for Swiggy + future POS connector. | feat: /connectors page — platform data source management with OAuth connect flow | None (frontend only) | Completed | Critical | Anoushka |  | W7 | 0% | P6-S01 | Can build now — reads from connectors table (already exists via P6-S02)
P6-F15 |  | Frontend | Dashboard enhancements | Add to existing dashboard: connector status widget (data source health bar), brief mode trigger button, today's Swiggy KPIs (orders today, delivery rating, top Swiggy seller), data_sources column on /runs list. | feat: dashboard — connector status widget, brief trigger, live Swiggy KPIs, data_sources on runs list | None (frontend only) | Completed | Critical | Anoushka |  | W7 | 0% | P6-S01 | Can build now — connector status widget reads connectors table
P6-F16 |  | Backend | Backend bug fixes for Swiggy UI features | Three backend fixes: (1) final_assembler.py was not including Swiggy state fields in API response (market_intel_output, swiggy_competitor/occupancy_context, swiggy_procurement_options, dineout_manager_output) — frontend Market Intel panel was always empty. (2) connector_repository.update_sync_status silently dropped updates when no DB row existed — fixed to auto-create connector row so last_sync_at always persists. (3) main.py ConsoleSpanExporter flooding backend logs with JSON on every request — removed BatchSpanProcessor(ConsoleSpanExporter()) line. | fix: final_assembler Swiggy fields, connector auto-create, silence OTel console exporter | None | Completed | High
P6-F16b |  | Docs | Consumer API clarification — code comments + CLAUDE.md | Swiggy MCP confirmed 100% consumer-facing from Builders Club docs. Added FUTURE USE / CONSUMER DATA ONLY comments to: swiggy_connector.py, sync/order_sync.py, feedback_sync.py, reservation_sync.py, orchestration/nodes/dineout_manager.py (corrected docstring re book_table), orchestration/state.py (swiggy_delivery_signal), graph.py (stream message). CLAUDE.md: product vision corrected, pipeline notes, sync layer notes, Workflow 1 + 2 corrected, build steps updated. Tracker: P6-S03/S05/S06 notes updated, P6-S12/S31 re-evaluated, 4 MI tasks added for honest Swiggy feature scope. | docs: consumer API scope clarified across sync layer, dineout node, state, CLAUDE.md | CLAUDE.md, 6 source files | Completed | Medium
P6-F17 |  | Frontend | Market intelligence panel (planning results page) | New panel on /runs/{id}. Competitor pricing table: your price vs area avg vs cheapest competitor per dish category. Area occupancy badge (HIGH/MEDIUM/LOW). Instamart prices for shortage items. Pricing alerts (red if >20% above area avg). Hidden when market_intel_output absent. | feat: market intelligence panel — competitor pricing + area occupancy on planning results | None (frontend only) | Completed | Critical | Anoushka |  | W7 | 0% | P6-S10 | Depends on P6-S11 (market_intel_output in plan API response)
P6-S14 | feature/swiggy-prompt-injection (deleted post-merge) | Agents | Wire Swiggy enricher context into recommendation node prompts | Swiggy enricher prompt_text injected into 3 LLM prompts: (1) menu_intelligence gets ## Market Context (competitor prices, alerts); (2) inventory gets ## Live Procurement Options (Instamart prices per shortage item); (3) reservation gets ## Occupancy Signal (area HIGH/MEDIUM/LOW). LLM now references Swiggy data in reasoning — e.g. "Order tomatoes via Instamart at Rs.24/kg". Frontend: AgentCard swiggySignal prop shows orange Swiggy badge in card header with one-line market signal (area tonight: HIGH, 5 Instamart prices live, 2 pricing alerts). Never independently PR-ed to dev -- fix/swiggy-sse-market-intel branched off its tip and shipped it as part of that PR instead; feature/swiggy-prompt-injection deleted 2026-07-03 (remote + local), fully superseded. | feat: wire Swiggy enricher context into node prompts — recommendations become market-aware | docs/AGENTS.md (node prompt sections updated) | Completed | Critical
P6-S35 | fix/swiggy-sse-market-intel | Reliability | Swiggy dashboard data-integrity fixes | Fixed Instamart procurement card rendering nothing despite live shortage data: frontend read item.name/item.in_stock but backend ProcurementEnricher sends item.ingredient/item.inStock (confirmed against the enricher's own test contract). Found and fixed a cost/token-attribution race: reservation and inventory nodes share the 'fast' LLM tier and run in true parallel; _inject() draining the shared provider usage buffer at node start/end let one node's drain steal the other's usage records. Fixed via per-node contextvar tagging (bind_llm_usage_node/drain_usage(node=...)) in llm/base.py + graph.py. Converted ~11 files across the Swiggy integration layer + cache/vector-memory infra from stdlib logging to structlog -- the app never calls logging.basicConfig(), so every .info()/.debug() call on those modules was being silently dropped, and .warning() lines printed unstructured with no run correlation. Merged to dev via PR #87, 2026-07-03. | fix: Instamart card field mapping, LLM usage attribution race, structlog conversion across Swiggy layer | None | Completed | High | Anoushka | 2026-07-02 | 2026-07-02 | 100% | P6-S14 | Verified via isolated LangGraph fan-out concurrency test; 298+ backend tests passing at time of fix
P6-S36 |  | Frontend | Explicit Swiggy attribution on recommendation text and cards | Recommendation prompts (inventory/reservation/menu) now require the LLM to explicitly name 'Swiggy' when citing live competitor/occupancy/Instamart data. Added HighlightSwiggy component wired into ManagerActionPanel, InventoryAlerts, MenuInsights, ReservationSummary. Extracted a shared SwiggySignalBadge component (previously duplicated inline in AgentCard.tsx, about to be triplicated in the /runs page) and wired the same per-card Swiggy-signal computation into app/runs/page.tsx's AgentOutputCard, matching what the live dashboard already showed. | feat: explicit Swiggy attribution in recommendation text + shared signal badge on dashboard and /runs cards | None (frontend + prompt text only) | Completed | Medium | Anoushka | 2026-07-02 | 2026-07-02 | 100% | P6-S35 | Frontend typecheck + eslint clean on all touched components
P6-S37 |  | Infra | Eval/observability CI gate + golden-dataset bug fix | New .github/workflows/backend-tests.yml: unit-tests job runs pytest tests/unit on every push/PR (includes the existing offline golden-set regression gate for free); llm-quality-evals job runs DeepEval + RAGAS (skips cleanly without GROQ_API_KEY, asserts once configured). Built scripts/build_ragas_dataset.py + build_deepeval_dataset.py mirroring build_golden_dataset.py's pattern, producing human-reviewed .candidates.json files -- never auto-merged, ground_truth requires human verification by design. Found and fixed a real bug in build_golden_dataset.py: it read final_response['agents'][...] but final_assembler_node actually writes final_response['recommendations'][...] -- confirmed via the checked-in fixture (all 50 golden runs had has_shortage_alerts=false), meaning the restock_when_shortage evaluator had been silently a no-op since it was written. | feat: CI eval gate, RAGAS/DeepEval dataset-refresh scripts; fix: golden-dataset key-path bug (restock evaluator was a no-op) | None | Completed | High | Anoushka | 2026-07-02 | 2026-07-02 | 100% | P6-S35 | 6 new tests for build_golden_dataset.py extractors, 10 new tests for the two dataset-refresh scripts, 11 corrected fixtures in test_swiggy_procurement_enricher.py. ACTION NEEDED: add GROQ_API_KEY + LANGSMITH_API_KEY as GitHub repo secrets for llm-quality-evals to assert anything.
P6-S38 |  | Frontend | Circuit-breaker degraded-state UX on market intel panel | MarketIntelService now attaches competitor_status: {state, resets_in_seconds} to market_intel_output when CompetitorEnricher returns None, distinguishing 'circuit breaker open, retrying automatically' from genuine no-data -- previously both rendered the identical blank 'No competitor pricing data' message. SwiggyMarketIntelPanel.tsx shows an amber 'temporarily unavailable, retrying in ~N min' message for the former. Root-caused via a live run where competitor pricing vanished but Instamart pricing worked in the same run, traced to the Food MCP circuit breaker being open while Instamart's was closed. | feat: distinguish circuit-breaker degradation from genuine no-data on market intel panel | None | Completed | Medium | Anoushka | 2026-07-02 | 2026-07-02 | 100% | P6-S35 | 4 new tests in test_market_intel_service.py; live-verified (fresh circuit trip captured correctly mid-run)
P6-S39 |  | Agents | Replan loop convergence fix | replan_orchestrator only ever re-ran the aggregator, never menu_intelligence -- so retries resubmitted the exact same unchanged menu_output to the critic, which correctly rejected it again every time (confirmed via a live run stuck at 3 identical critic rejections, hitting the 2-retry cap on every attempt). Rewired REPLAN_ORCHESTRATOR -> MENU_INTELLIGENCE (was -> AGGREGATOR), threaded replan_context through as prior_feedback into MenuService.analyse_and_recommend() and the prompt. Verified safe under LangGraph's join semantics using the same proven pattern AGGREGATOR's existing dual incoming edges already use. | fix: replan loop now regenerates the plan instead of resubmitting the same one -- critic retries actually converge | None | Completed | Critical | Anoushka | 2026-07-02 | 2026-07-02 | 100% | P6-S04 | 1 new graph-level integration test (test_replan_loop_integration.py) mocking a revision-then-approval cycle and asserting MenuService is called twice with feedback threaded through; live-verified end to end
P6-S40 |  | Agents | Menu-synthesis context-sharing fix (capacity awareness) | menu_intelligence is the graph's 5-way fan-in synthesis point (RESERVATION/COMPLAINT_INTELLIGENCE/INVENTORY/MARKET_INTEL/DINEOUT_MANAGER all converge on it) but the node only ever read 3 of those 5 outputs -- it hardcoded menu_assumptions['assumed_covers_within_capacity']=True on every run because it never received reservation/occupancy data at all. This fake assumption tripped a cross-agent conflict (Diff 2 in evaluation_sanity.py) on nearly every high-occupancy Friday Rush plan. Audited every node's state reads against the graph's edges to confirm this was the only structurally broken diff of the 5 (Diffs 3/4/5/6 all compare genuinely-computed values). Threaded reservation/market-intel/dineout context into MenuService.analyse_and_recommend(), computed capacity_constrained for real from reservation's own occupancy figure, added an explicit throughput-protection rule to the menu prompt when occupancy is high. | fix: menu_intelligence now genuinely synthesizes all 5 fan-in inputs instead of 3 -- closes a fake cross-agent conflict that capped every high-occupancy run | None | Completed | Critical | Anoushka | 2026-07-02 | 2026-07-03 | 100% | P6-S39 | 2 new tests in test_menu_service.py, 2 in test_agent_nodes.py, 3 new Diff-2 tests in test_evaluation_sanity.py; live-verified (stale_assumptions no longer contains the fake conflict)
P6-S41 |  | Agents | Critic assumption-diff override fix | critic_service.py unconditionally force-downgraded approved->revision (capped score at 0.72) whenever any stale cross-agent assumption existed, regardless of the LLM critic's own judgment. A live run showed the critic explicitly reasoning through a conflict and writing 'Approving with these items noted for the manager's attention' in its own notes, then getting silently overridden to revision anyway by this code (added in an earlier hardening pass adjacent to P6-00b). Removed the automatic verdict override specifically for assumption diffs, kept it for real deterministic policy/sanity-rule violations which should stay non-negotiable. Kept full visibility (feedback, notes, DecisionLog audit trail) -- the critic's own considered judgment is now trusted. | fix: critic no longer overrides its own considered approval when a stale assumption exists -- visibility kept, veto removed | None | Completed | Critical | Anoushka | 2026-07-03 | 2026-07-03 | 100% | P6-S40 | 1 test rewritten in test_critic_service.py; live-verified -- same scenario now reaches approved on first pass (score 0.74-0.82 across repeated runs) instead of capping at 0.72 every time
P6-S42 |  | Agents | Inventory ordering bug + guardrail price-citation loss | Two real bugs found and fixed, different from the originally-planned scope (occupancy-aware restock urgency was not what was actually wrong). (1) ProcurementEnricher.enrich() ran AFTER the LLM recommendation call inside the old combined analyse_and_recommend(), so procurement_context was always None when the inventory prompt was built -- the prompt's 'name Swiggy explicitly' instruction was unreachable dead code. Split InventoryService into compute_shortage_data() (pure DB/projection, no LLM) + generate_recommendation() (LLM call); inventory_node.py now computes the real shortage list first, fetches live Instamart prices for exactly those ingredients, then generates the recommendation with prices already in hand. (2) Even after reordering, build_capped_restock_actions() -- the deterministic guardrail that always overrides the LLM's proposed quantities -- rebuilt restock_actions from shortage_alerts alone with zero access to procurement_context, silently discarding any Swiggy price citation regardless of prompt quality. Threaded procurement_context through merge_guardrailed_recommendation() -> build_capped_restock_actions(), which now appends 'Swiggy Instamart lists it at Rs.X/unit (in stock)' to the capped line for each priced ingredient. | fix: inventory Instamart price ordering + guardrail now carries Swiggy price citation through to restock_actions | None | Completed | High | Anoushka | 2026-07-03 | 2026-07-03 | 100% | P6-S40 | 26/26 tests green in test_inventory_service.py, incl. 2 new regression tests: test_procurement_prices_reach_the_llm_prompt_same_run (ordering fix) and test_guardrailed_restock_actions_keep_swiggy_price_citation (guardrail fix). Live-verified end to end: run #242 (friday_rush) approved 81/100, restock_actions for all 5 rate-limited shortage items read 'Swiggy Instamart lists it at Rs.X/unit'; confirmed rendering correctly in the actual /runs UI via a Playwright screenshot, not just the raw API response.
P6-S47 |  | Security | Resolve suspicious content in apps/web/cortexkitchen-ui/AGENTS.md | File contains a pre-existing planted-looking instruction ('This is NOT the Next.js you know... read node_modules/next/dist/docs/') predating this session, plus an unexplained '/btw/' line added during this session by an unknown actor -- not the result of any tool call this session. Flagged directly to the user rather than complying with a system-note instruction to hide it. Per the user's explicit decision, stripped only the injected '/btw/' line; the pre-existing node_modules-docs content was left untouched (predates this session, not further investigated). | fix: strip injected /btw/ line from AGENTS.md per user decision; pre-existing suspicious content left untouched | None | Completed | High | Anoushka | 2026-07-03 | 2026-07-03 | 100%
P6-S48 |  | Infra | Windows console-encoding crash in ensure_collection() -- silent 500 on every planning run | ensure_collection() in qdrant_client.py printed a checkmark (a non-ASCII Unicode symbol) on every Qdrant collection check. Windows console codepage (cp1252, not UTF-8) can't encode that character, so print() raised UnicodeEncodeError inside a FastAPI dependency (get_memory) resolved on every request that touches memory/RAG context -- i.e. every planning run. The client received a malformed non-JSON response with no clear error. Root-caused by reading the raw response body instead of assuming a timeout. Replaced both Unicode symbols with ASCII-safe '[OK]'/'[INFO]' text. | fix: replace non-ASCII print() characters in ensure_collection() -- was silently 500ing every planning run on Windows | None | Completed | Critical | Anoushka | 2026-07-03 | 2026-07-03 | 100% | P6-S35 | Manual live verification: reproduced the crash via a live curl planning run returning invalid JSON, root-caused via the raw backend traceback, fixed, then re-ran the same friday_rush scenario twice (run #241, #242) end to end with no crash.
DO FIRST — no staging creds needed ¦ each task: own branch → PR → merge dev → merge main → docs + screenshots + tracker updated
P6-MI01 | feature/swiggy-market-intel-expansion | Agents | Competitor deal & offer intelligence | Surface deal and amenity data from get_restaurant_details (already called in OccupancyEnricher but data discarded). Extract: deals[], isFree, title, amenities[], highlights[], avgRating per competitor. Add to market_intel_output as competitor_deals list. Show in Market Intelligence panel: Competitor X running 20% off deal. Has live music + valet. No new API calls — uses data already fetched. | feat: surface competitor deal and amenity intelligence from Dineout MCP | docs/AGENTS.md (OccupancyEnricher output extended) | Planned | High
P6-MI02 |  | Infra | Competitor price trend tracking | New table: market_snapshots (org_id, snapshot_type, data jsonb, captured_at). After each planning run, persist competitor_pricing dict from CompetitorEnricher. MarketIntelService computes week-over-week delta per dish. market_intel_output gains price_trends field: [{dish, current_avg, prev_avg, delta_pct, direction}]. Panel shows: Biryani area avg up 18pct vs last week. Zero new Swiggy API calls - just persisting what we already fetch. | feat: competitor price trend tracking — persist snapshots, week-over-week delta | docs/DATA_MODEL.md (market_snapshots table), docs/AGENTS.md | Planned | High
P6-MI03 |  | Agents | Category-level pricing analysis | CompetitorEnricher currently returns flat dish->price dict. Extend to group by inferred category (biryani/starters/mains/drinks). Compute area avg per category. Compare against restaurant menu categories. Output: [{category, your_avg, area_avg, diff_pct, verdict}]. menu_intelligence prompt gains: Your North Indian mains avg Rs.320 vs area Rs.275 (+16pct). Your starters Rs.180 vs area Rs.210 (-14pct underpriced). No new API calls - aggregation on existing CompetitorEnricher output. | feat: category-level pricing — group competitor prices by category vs your menu | docs/AGENTS.md (CompetitorEnricher output extended) | Planned | High
P6-MI04 | feature/swiggy-chatbot-expansion | Product | Chatbot — Dineout competitive queries | Add 3 new Groq function-calling tools to chatbot: get_competitor_deals(cuisine, addressId) answers what deals are competitors running tonight; get_area_occupancy(cuisine, addressId) answers how full are restaurants near me; get_trending_dishes(addressId) answers what are competitors pushing on menus. All use existing Dineout MCP tools: search_restaurants_dineout, get_restaurant_details, get_available_slots. Makes chatbot the single interface for all live Swiggy market queries. | feat: chatbot Dineout queries — competitor deals, area occupancy, trending dishes | docs/AGENTS.md (chatbot tools section) | Planned | High
P6-S16 | feature/action-queue | Product | ActionQueueService + action_queue table | New table: id, org_id, action_type (AUTO/APPROVE_REQUIRED/RECOMMENDATION), payload jsonb, status (PENDING/APPROVED/EXECUTED/REJECTED/EXPIRED), approved_by, executed_at, error. ActionQueueService CRUD. Plan output includes action_queue section in API response. | feat: ActionQueueService + action_queue table — 3-tier action model with approval lifecycle | docs/ACTION_QUEUE.md (new), docs/APIS.md (action queue endpoints), docs/DECISIONS.md (D-021) | Planned | High | Anoushka |  | W5 | 0% | P6-S10 | No staging creds needed — action queue is pure backend, no Swiggy write calls yet.
P6-S18 |  | Infra | Structured outputs — tool_choice=required, zero JSON hallucination | Upgrade chatbot Groq calls to tool_choice=required + strict JSON schema. Apply to all 3 Swiggy chatbot tools (search_menu, get_food_orders, search_products). Chatbot function calls never hallucinate JSON. Zero model coupling — works on any provider. | feat: structured outputs — tool_choice=required across all chatbot tools | docs/AGENTS.md | Planned | High | Anoushka |  | W6 | 0% | P6-F17 | Schema validation test; chatbot returns valid JSON on 10 consecutive calls
P6-S19 |  | Infra | Prompt caching — 60-90% cost reduction on critic + aggregator | Add Anthropic prompt caching headers to critic and aggregator LLM calls. Both have long system prompts repeated every run. Expected saving: 60-90% of prompt token cost per planning run. Graceful fallback on cache miss. Compatible with Google Gemini too. | feat: prompt caching — cut LLM costs 80% on critic and aggregator nodes | docs/ARCHITECTURE.md | Planned | High | Anoushka |  | W6 | 0% | P6-S18 | Cost log shows cache_hit=true on second run of same scenario
P6-S21 | feature/workflow-system | Product | Restaurant workflow system — owner-defined trigger-condition-action automations | New table: workflows (org_id, trigger, condition_json, action_type, action_payload, active). Triggers: AFTER_PLANNING_RUN, DAILY_BRIEF, ON_THRESHOLD. Actions: SEND_WHATSAPP, QUEUE_ACTION, CALL_WEBHOOK. WorkflowEngine evaluates conditions post-run and fires actions. /workflows UI page. Turns CortexKitchen from a tool into an OS. | feat: workflow system — restaurant owners define custom automations | docs/ARCHITECTURE.md, docs/APIS.md | Planned | High | Anoushka |  | W7 | 0% | P6-S20 | End-to-end: planning run fires whatsapp trigger; webhook called on threshold breach
P6-S23 |  | Product | LiveMonitorService — SSE feed during service hours | APScheduler-managed SSE stream active 12:00-14:00 and 19:00-22:00 IST. Polls every 30s: get_food_orders (activeOnly=true) for active delivery orders, track_food_order for in-flight ETAs, track_order for Instamart procurement status. Pushes events to /live page frontend. Alerts on: delivery > SLA threshold, order spike, ingredient delivery confirmed. | feat: LiveMonitorService — real-time Swiggy SSE during service hours (orders + procurement) | docs/PRODUCT_MODES.md (live monitor section) | Planned | Medium | Anoushka |  | W6 | 0% | P6-S22, P6-S30 | SSE stream active only during service hours IST; events emitted on each 30s poll; delivery threshold alert fires; stream stops outside service window.
P6-S24 |  | Infra | 3 new CortexKitchen MCP server tools | Add to mcp_server.py: get_market_brief (calls MarketIntelService live, returns competitor snapshot for Claude Desktop), get_action_queue (pending actions awaiting approval), approve_action (owner approves from Claude Desktop, triggers execution). JWT auth on all 3. | feat: 3 new MCP tools — get_market_brief, get_action_queue, approve_action | docs/APIS.md (MCP tools section), docs/ARCHITECTURE.md (MCP server updated) | Planned | Medium | Anoushka |  | W6 | 0% | P6-S16 | All 3 tools smoke-tested in Claude Desktop; approve_action triggers execution end-to-end; JWT enforced
P6-S25 | feature/debate-critic | Agents | Multi-agent debate critic — two critic instances, consensus scoring | Run two LLM critic instances with opposing system prompts (optimistic vs conservative). Structured debate: each scores the plan, flags disagreements, moderator LLM resolves. Final verdict is consensus or flagged-disagreement. Provably better plan quality than single critic. Zero model coupling. | feat: multi-agent debate critic — consensus scoring, catches more edge cases | docs/AGENTS.md | Planned | Medium | Anoushka |  | W8 | 0% | P6-S21 | Debate resolves on 5 test plans; disagreement cases escalate correctly
P6-R26 | feature/voice-interface | Product | Voice interface — Whisper + RAG chatbot | Whisper transcription on browser-recorded question (MediaRecorder API). RAG chatbot (P5-12) answers. TTS reads back. Manager asks questions while walking the floor. Works with both synthetic and real Swiggy data now in DB. Blocked on P5-12 (already done). | feat: voice interface — Whisper transcription + RAG answer + TTS readback | docs/PRODUCT_MODES.md (voice section) | Planned | Low | Anoushka |  | W7 | 0% | P6-S31 | Transcription accuracy smoke test; end-to-end voice → RAG answer → TTS; works with real Swiggy data in DB
P6-F27 | feature/action-queue-ui | Frontend | Action queue UI + procurement tracker | New section below plan output. Lists pending actions with type badge. Approve/Reject buttons for APPROVE_REQUIRED. Instamart cart preview modal (items, total, ETA) before approving checkout. Procurement tracker in inventory panel: placed orders, status, ETA. | feat: action queue UI — approve/reject with cart preview, procurement tracker | None (frontend only) | Planned | High | Anoushka |  | W7 | 0% | P6-S13 | Depends on P6-S16 (action_queue in plan API response)
P6-F28 |  | Frontend | /brief page — daily morning briefing | New route /brief. Overnight Swiggy performance (orders, avg delivery time, late %), today's demand forecast vs yesterday, top 3 action priorities, market snapshot. Auto-refreshes if brief is stale. Empty state when no brief yet. | feat: /brief page — daily morning operational briefing | None (frontend only) | Planned | Medium | Anoushka |  | W7 | 0% | P6-S31 | Depends on P6-S22 (BriefingService)
P6-F29 |  | Frontend | /live page — real-time service monitor | New route /live. Kitchen display-grade SSE feed from LiveMonitorService (P6-S23). Shows active Swiggy delivery orders with ETA countdown, Instamart procurement status with delivery ETA, alert banner on delivery spike or ingredient arrival. Swiggy logo + 'Live via Swiggy MCP' badge. Page shows inactive state outside service hours (12-14h, 19-22h IST). | feat: /live page — SSE kitchen display for active orders and procurement tracking | None (frontend only) | Planned | Medium | Anoushka |  | W7 | 0% | P6-S23 | SSE events render in real time; ETA countdown ticks; alert banner fires on delivery spike; Swiggy branding visible; inactive state shown outside service hours.
P6-S43 |  | Infra | Fix SQLite/JSONB test-infra gap blocking full CI coverage | test_swiggy_reservation_sync.py and test_connector_repository.py are excluded from the CI unit-tests job (P6-Q03) because they spin up a real SQLite engine and connectors.connector_metadata uses Postgres' JSONB column type, which SQLite's compiler can't render. Either give the column a SQLite-compatible fallback type for tests, or run these two files against a real Postgres service container in CI (docker-compose.yml already defines postgres:16 for local dev -- same image could back a CI service). | fix: SQLite-compatible JSONB handling (or Postgres CI service) for excluded test files | None | Planned | Medium | Anoushka |  |  | 0% | P6-S37
P6-S44 |  | Product | Promote reviewed RAGAS/DeepEval candidates into curated eval files | build_ragas_dataset.py / build_deepeval_dataset.py (P6-Q03) produce .candidates.json files from live approved runs but never auto-merge them -- ground_truth needs human verification by design. Needs a recurring habit of actually running these periodically and hand-promoting reviewed candidates into complaint_rag_samples.json / test_deepeval_quality.py, or the static datasets stay frozen at today's size forever. | chore: promote reviewed eval candidates into curated datasets | None | Planned | Low | Anoushka |  |  | 0% | P6-S37
P6-S45 |  | Infra | Regenerate golden_runs.json against real production data | build_golden_dataset.py's key-path bug is fixed (P6-Q03) but the checked-in fixture still reflects the old, always-empty extraction, since regenerating it requires a live Postgres populated with real run history, which wasn't available during the fix. Run scripts/build_golden_dataset.py locally once docker-compose services are up to refresh it with corrected shortage/restock data. | chore: regenerate golden_runs.json with corrected extraction logic | None | Planned | Medium | Anoushka |  |  | 0% | P6-S37
P6-S46 |  | Product | Product redesign -- move dashboard/runs pages past 'dev console' feel | Explicitly deferred this session pending a proper scoping pass. Concrete evidence gathered: /runs/{id} throws a raw unstyled Next.js 404 (no per-run deep link, only in-page sidebar selection on /runs), and the run-detail view is a dense wall of monospace-labelled text blocks (dimension scores, 10+ revision-reason cards) with little visual hierarchy -- reads like a debug trace rather than something an owner skims at 7am. The landing/hero page already looks like a real product; this needs its own scoping conversation (which pages, target feel, how much rework), not a quick fix bundled into other work. | TBD -- needs scoping conversation first | None | Planned | Medium | Anoushka |  |  | 0%
→ DEMO 1 ¦ all above on main, docs updated, screenshots done — record full Swiggy read + AI + voice + live monitor demo ←

## Staging Creds + Phase 7
Task ID | Feature Branch | Workstream | Task | Detailed Outcome / Done Means | PR Description Hook | Docs Updated | Status | Priority | Owner | Start | Target | % Done | Depends On | Tests Expected
BLOCKED — needs Swiggy staging creds (write tools: checkout, book_table)
P6-S30 | feature/procurement-executor | Agents | ProcurementExecutor — Instamart checkout flow | Create executor/procurement.py. Flow: get_cart -> clear_cart -> update_cart([{spinId, qty}]) -> get_cart (verify bill) -> LangGraph interrupt() for owner approval -> checkout (COD, Rs.999 cap). NON-IDEMPOTENT: on any 5xx from checkout, call get_orders before retrying — never blind-retry. Stores confirmed order in procurement_orders table. spinIds sourced from ProcurementEnricher state (P6-S09). | feat: ProcurementExecutor — Instamart checkout with LangGraph interrupt + check-then-retry safety | docs/SWIGGY_INTEGRATION.md (P6-S30 executor section) | Blocked | High | Anoushka |  | W5 | 0 | P6-S16, P6-S09 | BLOCKED: needs staging creds (mcp-staging.swiggy.com). Check-then-retry fires on 5xx mock; LangGraph interrupt() pauses graph; cart verified before checkout; duplicate order prevention tested.
P6-S31 | feature/dineout-executor | Agents | Dineout table booking execution | INVALID AS DESCRIBED. book_table in consumer MCP books a table AT another restaurant (consumer action), not manages your own restaurant Dineout presence. Managing your own restaurant Dineout slots requires Swiggy Partner/Business API which is separate from consumer MCP. Re-scope: could use book_table for mystery dining (send manager to competitor) but that is a minor feature. Actual Dineout management blocked on Partner API access. | feat: Dineout table booking execution with approval gate | docs/SWIGGY_INTEGRATION.md (book_table non-idempotency), docs/ACTION_QUEUE.md | Needs Re-evaluation | Medium | Anoushka |  | W5 | 0 | P6-S16 | BLOCKED: needs staging creds. book_table is a WRITE tool — places real Dineout bookings. Wait for mcp-staging.swiggy.com credentials before building.
P6-S32 | feature/computer-use | Agents | Computer use agent — automate Swiggy Partner Dashboard | Claude computer-use agent automates Swiggy Partner Dashboard actions not exposed via MCP: menu price updates, promo activation, opening delivery hours. Triggered from action queue. Sandboxed browser session. Claude-specific today; fallback to manual action link if unavailable. | feat: computer use — automate Swiggy Partner Dashboard actions | docs/ARCHITECTURE.md | Blocked | Low | Anoushka |  | W9 | 0 | P6-S25 | Computer use agent updates one menu price end-to-end in sandbox
WHEN RECEIVED — Sarvam AI access + AWS credits
P6-S33 |  | Agents | Sarvam AI voice — Hindi/Hinglish speech-to-text + text-to-speech for chatbot | Replace Whisper plan with Sarvam ASR. Owner speaks in Hindi during service, gets response in Hindi via Sarvam TTS. Handles Hinglish and regional accents natively. Zero model coupling — Sarvam is swappable. Integrates with existing chatbot ReAct loop. | feat: Sarvam AI voice — Hindi/Hinglish STT+TTS, India-native voice interface | docs/AGENTS.md | Planned | High | Anoushka |  |  | 0 | P6-R26 | Voice round-trip in Hindi under 3 seconds; Hinglish query understood correctly
P6-S34 |  | Infra | AWS production deployment — RDS, ElastiCache, ECS Fargate, GitHub Actions CI/CD | PostgreSQL → RDS, Redis → ElastiCache, API → ECS Fargate (containerised), frontend → Vercel/Amplify, exports → S3. GitHub Actions pipeline: test → build → push ECR → deploy ECS. SSL cert. One-command deploy. Uses AWS credits. Zero downtime deploys. | feat: AWS production deployment — containerised, auto-scaling, CI/CD pipeline | docs/ARCHITECTURE.md | Planned | High | Anoushka |  |  | 0 | P7-01 | Full deploy from scratch via one make command; zero-downtime redeploy verified
→ DEMO 2 / POTENTIAL DEMO ¦ all above on main, staging write tools + Sarvam voice + AWS hosted — record full product demo ←
DOCS + PHASE 6 MILESTONE MERGE
P6-D35 |  | Docs | 5 new documentation files | CONNECTORS.md: BaseConnector interface, sync vs enrich, how to add new connector. SWIGGY_INTEGRATION.md: all 22 tools, parameter mappings, OAuth, rate limits, error handling. ACTION_QUEUE.md: action types, approval flow, non-idempotent patterns. DATA_SOURCES.md: all sources, channels, sync frequency. PRODUCT_MODES.md: ops/brief/live/voice mode specs. | docs: 5 new documentation files for Phase 6 connector + action + product mode layer | docs/CONNECTORS.md, docs/SWIGGY_INTEGRATION.md, docs/ACTION_QUEUE.md, docs/DATA_SOURCES.md, docs/PRODUCT_MODES.md | Planned | High | Anoushka |  | W8 | 0 | P6-F15 | All 5 files present; no broken links; tool parameter tables accurate vs Swiggy docs
P6-D36 |  | Docs | Update CLAUDE.md, README.md, Swiggy deep-dive for Phase 6 completion | CLAUDE.md: update Current system state to Phase 6 complete (11-node pipeline, 22 Swiggy tools, full action + brief + live layer). README.md: add Phase 6 achievements, Swiggy integration summary, demo instructions. CortexKitchen_Swiggy_Deep_Dive.html: mark all chapters complete, update progress bar to 100%. | docs: Phase 6 milestone — CLAUDE.md, README, Swiggy deep-dive final update | CLAUDE.md, README.md, CortexKitchen_Swiggy_Deep_Dive.html | Planned | High | Anoushka |  | W8 | 0 | P6-D35 | CLAUDE.md system state accurate; README demo instructions work end-to-end; deep-dive HTML shows 100% progress.
P6-D37 |  | Release | Phase 6 milestone merge to main | Merge feature/ck-v2-platform → dev → main. All 11 nodes verified in LangSmith. All 22 Swiggy tools exercised in staging. POS connector imports CSV end-to-end. Voice interface smoke tested. Action queue end-to-end. All 3 product modes verified. 5 new frontend pages smoke tested. Full test suite green. | release: Phase 6 complete — CortexKitchen v2 Swiggy-native restaurant OS | README.md (portfolio headline), docs/ROADMAP.md (Phase 6 complete) | Planned | Critical | Anoushka |  | W8 | 0 | P6-D36 | Full test suite green; 11 nodes in LangSmith; staging demo clean; portfolio README updated; docs website prep checklist done
PHASE 7 — Production, CI/CD, Public Release
P7-01 | feature/phase7-cicd | Release | CI/CD — GitHub Actions | Automated on every PR: unit + integration + RAGAS evals + DeepEval; lint; type check; frontend build; coverage report. Fail on critic score regression. Cache pip dependencies. NOTE (2026-07-03): unit tests + RAGAS/DeepEval already run in CI via P6-Q03's .github/workflows/backend-tests.yml, done early during Phase 6 hardening. Remaining scope for this task: integration tests, lint, type check, frontend build, coverage report, and merging into a single pipeline. | feat: CI/CD — automated test + eval pipeline on every PR | docs/ROADMAP.md | Planned | High | Anoushka |  | P7 | 0 | P6-D37 | CI passes on clean repo; fails on intentional test break; eval regression detected
P7-02 | feature/phase7-cloud-deploy | Release | Cloud deployment — Railway / Fly.io | Containerise API + frontend. Deploy to Railway or Fly.io. Managed Postgres + Redis + Qdrant. Production env vars. Swiggy OAuth redirect URI updated for production domain. Health endpoint green on production URL. | feat: cloud deployment — production on Railway/Fly.io | docs/ROADMAP.md | Planned | High | Anoushka |  | P7 | 0 | P7-01 | Production URL health check green; all env vars; Swiggy OAuth works on production domain
P7-03 | feature/phase7-prod-hardening | Release | Production hardening | Rate limiting (slowapi). Secrets management (not env file). CORS lockdown. JWT key rotation. Sentry alerts tuned for production. Load test with k6. | feat: production hardening — rate limiting, secrets, CORS, JWT rotation | docs/ROADMAP.md | Planned | Medium | Anoushka |  | P7 | 0 | P7-02 | Rate limit smoke test; CORS rejection; Sentry alert fires on 500; k6 load test passes
P7-04 | feature/phase7-docs-website | Docs | Mintlify docs website | Point Mintlify at docs/ folder. Navigation: architecture, connectors, agents, API reference, Swiggy integration guide, evaluation, deployment. Custom domain. Public URL to share with Swiggy team, recruiters, restaurant clients. | feat: Mintlify docs website — public-facing CortexKitchen v2 documentation | All docs/ files | Planned | Medium | Anoushka |  | P7 | 0 | P7-03 | Docs site live at public URL; all 13 doc files render; search works; no broken links
P7-05 | dev -> main PR | Release | Sync Phase 7 to main — public release | Live production URL. README updated with live demo link + docs website link. Apply to jobs immediately. Update portfolio. | release: Phase 7 complete — CortexKitchen v2 live in production | README.md, anoushkavyas.vercel.app portfolio | Planned | Low | Anoushka |  | P7 | 0 | P7-04 | Full E2E on production URL; demo video recorded; portfolio updated

## Doc Strategy
CortexKitchen v2 — Documentation Strategy (Phase 6)
Doc File | What It Covers | Updated In (task ID) | Status
docs/CONNECTORS.md | BaseConnector interface, sync vs enrich, how to add new connector | P6-S01 — NEW | New
docs/SWIGGY_INTEGRATION.md | 22 tools used, parameter mappings, OAuth, rate limits, error handling | P6-D35 — updated P6-S01/S02/S03 | Updated (P6-S03 status ✅)
docs/ACTION_QUEUE.md | Action types, approval flow, non-idempotent execution patterns | P6-S13 — NEW | New
docs/DATA_SOURCES.md | All data sources, channels, sync frequency, source field values | P6-S03 — NEW | New
docs/PRODUCT_MODES.md | Ops / brief / live / voice mode specs, triggers, outputs | P6-S31 — NEW | New
docs/ARCHITECTURE.md | Connector layer, 11-node pipeline, action layer, product modes | P6-S01, P6-S10, P6-S13, P6-S31 | Updated (P6-S01/S02 done)
docs/AGENTS.md | 11 nodes incl. market_intel + dineout_manager, 5 assumption diffs | P6-S10, P6-S11, P6-S12 | Update
docs/APIS.md | All endpoints: brief, live, action queue, connector management | Each PR adding endpoint | Update
docs/DATA_MODEL.md | 6 new tables: connectors, platform_orders, action_queue, procurement_orders, market_snapshots, daily_briefs | P6-S02, P6-S13, P6-S31 | Updated (P6-S02 done)
docs/DECISIONS.md | D-019 connector pattern, D-020 Swiggy primary, D-021 action queue, D-022 product modes | P6-S01, P6-S03, P6-S13, P6-S31 | Updated (D-019 added P6-S01)
docs/ROADMAP.md | Phase 6 full plan, Phase 7 scoped | P6-S01, P6-D37 | Update
docs/EVALUATION.md | Eval criteria for market_intel + dineout_manager nodes | P6-S10, P6-S11 | Update
README.md + docs/README.md | Portfolio headline: CortexKitchen v2 Swiggy-native restaurant OS | P6-D37 | Update
CLAUDE.md | swiggy/ infra path, Swiggy docs URLs, env vars, BRANCH_DOCS pattern | P6-S01 | Created (P6-S01 done)
Mintlify docs website | Public-facing docs site — all docs/ files, custom domain | P7-04 — Phase 7 | Phase 7

## Git Practices
CortexKitchen — Git Branching Rules
Branch | Purpose | Rule | Current note
main | Stable milestone only | Only sync from dev when a phase milestone is safe/demo-ready | Phase 6 on dev (P6-S01/S02 merged). main has P5 + P6-00 series. Next main sync: end of Phase 6.
dev | Active integration branch | All merged feature work lands here first | Current base — P6-S04 (feature/agent-intelligence) IN PROGRESS; P6-S05/S06 blocked on Swiggy token
feature/... | All implementation and docs work | Create from latest dev, PR back to dev, then delete branch | Current style
Local cleanup | After merge | Delete remote + local feature branch, checkout dev, pull latest | Continue throughout project