## Dashboard
CortexKitchen — Project Dashboard
Current milestone: Phase 6 — CortexKitchen v2 (Swiggy integration + platform expansion) | Connector layer, 11-node pipeline, action queue, 3 product modes, voice interface, POS connector
Last completed: P6-S03 — SwiggyOrderSyncService, get_food_orders → orders table (2026-06-27) | Assumption diffing merged; EvaluationSanityChecker O(N²)→O(N); 9 docs updated
Stable: dev through P6-S03; P6-S04 (agent-intelligence) IN PROGRESS → next: P6-S05 (Dineout sync, token pending) | Next: P6-S01 — BaseConnector + SwiggyMCPClient (Week 1)
Next recommended branch | feature/swiggy-base-connector
Phase | Status | % Complete | Key outcome
Phase 0 | Completed | 1 | Docs, roadmap, architecture, data model, APIs, evaluation, implementation plan
Phase 1 | Completed | 1 | API + Docker + DB + Seed + LLM + Core services + Qdrant complete+ langgraph skeleton + friday rush endpoint; dashboard complete; tests done
Phase 2 | Completed | 1 | Optimization layer: Prophet forecasting, inventory alerts, menu insights, and dashboard enhancementand evaluation refinement complete
Phase 3 | Completed | 1 | Advanced agentic features: auditable planning runs, richer critic evaluation, cost-aware scoring, and multi-scenario operational planning
Phase 4 | Completed | 1 | Productisation (no real data required): auth, LangSmith tracing, health checks, structured logging, LLM cost tracking, admin UI, runs UI, restaurant profiles, LLM provider swap, RAGAS evals, DeepEval, MCP server
Phase 5 | Completed | 1 | PDF/Excel export, frontend UX fixes, Redis cache, SSE streaming, what-if simulator, observability, evals, tenant isolation, email digest, RAG chatbot
Phase 6 | Planned | 0% | Swiggy-native restaurant OS: connector layer (Swiggy first, POS second), 11-node LangGraph pipeline, action queue with approval gates, 3 product modes (ops/brief/live), voice interface, 5 new frontend pages
Phase 7 | Planned | 0 | Production deploy: CI/CD, Railway/Fly.io, managed Postgres+Redis, production hardening, public release

## Phase Tracker
CortexKitchen — Phase Tracker (P0 through P6-S02 complete)
Phase 6 planned tasks (P6-01 onwards) live in the Phase 6 sheet · This sheet = historical record only
Phase | Order | Task ID | Workstream | Task | Detailed Outcome / Done Means | Branch | Status | Priority | Owner | Start | Target | Done | Progress % | Depends On | Tests Expected | PR / Notes
Phase 0
Phase 0 | 1 | P0-01 | Repo | Create repo + branches | GitHub repo created, main/dev set up, no direct work on main | feature/phase0-repo-scaffold | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% |  | Smoke check repo + branch flow | Merged to dev, later synced to main
Phase 0 | 2 | P0-02 | Docs | PRD + roadmap + decisions | Core product direction locked in docs | feature/phase0-architecture-docs | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-01 | Doc review | Merged to dev, branch deleted
Phase 0 | 3 | P0-03 | Docs | Architecture doc | System layers, flow, LLM/RAG strategy captured | feature/phase0-architecture | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-02 | Doc review | Merged to dev, branch deleted
Phase 0 | 4 | P0-04 | Docs | Agents + data model + APIs | Agent specs, DB model, API contracts documented | feature/phase0-agents-data-api | Completed | High | Anoushka | 2026-03-15 | 2026-03-15 | 2026-03-15 | 100% | P0-03 | Doc review | Merged to dev, branch deleted
Phase 0 | 5 | P0-05 | Docs | Evaluation + implementation plan | Evaluation rubric and build order finalized | feature/phase0-evaluation-plan | Completed | High | Anoushka | 2026-03-15 | 2026-03-16 | 2026-03-16 | 100% | P0-04 | Doc review | Merged to dev, branch deleted
Phase 1
Phase 1 | 7 | P1-01 | Backend | API scaffold | FastAPI app boots, settings, health endpoints, dependency checks, tests pass | feature/phase1-api-scaffold | Completed | High | Anoushka | 2026-03-16 | 2026-03-16 | 2026-03-16 | 100% | P0-06 | 3 unit tests + manual endpoint verification | Root, docs, /health, /health/dependencies verified
Phase 1 | 8 | P1-02 | Infra | Docker infra | docker-compose for Postgres, Qdrant, Redis; startup verified | feature/phase1-infra-docker | Completed | High | Anoushka | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | P1-01 | Service startup smoke tests | Merged to dev, branch deleted
Phase 1 | 9 | P1-03 | Backend | DB schema + models | Initial relational schema for reservations, orders, complaints, traces | feature/phase1-db-schema | Completed | High | Anoushka | 2026-03-21 | 2026-03-21 | 2026-03-21 | 100% | P1-02 | Schema tests / migrations sanity | Merged to dev, branch deleted
Phase 1 | 10 | P1-04 | Data | Seed data | Pizza-heavy synthetic data with Friday spikes and simulated reservation/review sources | feature/phase1-seed-data | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-03 | Seed script smoke tests | Merged to dev, branch deleted
Phase 1 | 11 | P1-05 | Backend | LLM provider layer | Base provider + Gemini provider , Groq Provider + prompt utilities | feature/phase1-llm-provider | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-01 | Provider unit/integration tests | Merged to dev, branch deleted
Phase 1 | 12 | P1-06 | Backend | Core services | Reservation analytics, baseline forecast, complaint summary, critic rules | feature/phase1-core-services | Completed | High | Anoushka | 2026-04-04 | 2026-04-04 | 2026-04-04 | 100% | P1-03 | Unit tests for services/rules | Merged to dev, branch deleted
Phase 1 | 13 | P1-07 | Memory | Qdrant memory | Collections, embeddings, retrieval helpers for complaints/SOPs | feature/phase1-qdrant-memory | Completed | Medium | Anoushka | 2026-04-05 | 2026-04-05 | 2026-04-05 | 100% | P1-02, P1-05 | Integration tests with retrieval | Merged to dev, branch deleted
Phase 1 | 14 | P1-08 | Agents | LangGraph skeleton | Shared state, nodes, graph edges, stub flow | feature/phase1-langgraph-skeleton | Completed | High | Anoushka | 2026-04-06 | 2026-04-06 | 2026-04-06 | 100% | P1-05, P1-06 | Graph flow tests | Merged to dev, branch deleted
Phase 1 | 15 | P1-09 | Backend | Friday rush endpoint | End-to-end planning endpoint + aggregated recommendation + trace write | feature/phase1-friday-rush-endpoint | Completed | High | Anoushka | 2026-04-08 | 2026-04-08 | 2026-04-08 | 100% | P1-06, P1-07, P1-08 | Integration + manual demo test | Merged to dev, branch deleted
Phase 1 | 16 | P1-10 | Frontend | Dashboard MVP | Planning result UI with forecast, complaint, critic, trace sections | feature/phase1-dashboard | Completed | Medium | Anoushka | 2026-04-10 | 2026-04-11 | 2026-04-11 | 100% | P1-09 | Frontend smoke tests | Merged to dev, branch deleted
Phase 1 | 17 | P1-11 | Quality | Phase 1 tests | Unit + integration + first E2E Friday rush flow | feature/phase1-tests | Completed | High | Anoushka | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | P1-09, P1-10 | Pytest + scenario checklist | Merged to dev, branch deleted
Phase 1 | 18 | P1-12 | Release | Sync Phase 1 to main | Stable MVP milestone on main | dev -> main PR | Completed | High | Anoushka | 2026-04-13 | 2026-04-13 | 2026-04-13 | 100% | P1-11 | Milestone verification | Main synced
Phase 2
Phase 2 | 19 | P2-01 | Forecasting | Prophet upgrade | Replace/add baseline with Prophet forecasting path | feature/phase2-prophet-upgrade | Completed | Medium | Anoushka | 2026-04-16 | 2026-04-17 | 2026-04-19 | 100% | P1-12 | Forecast comparison tests | Merged to dev, branch deleted
Phase 2 | 20 | P2-02 | Ops | Inventory alerts | Shortage/overstock alerts using forecast + stock levels | feature/phase2-inventory-alerts | Completed | Medium | Anoushka | 2026-04-19 | 2026-04-19 | 2026-04-20 | 100% | P2-01 | Rule tests | Merged to dev, branch deleted
Phase 2 | 21 | P2-03 | Menu | Menu insights | Top/weak items and promo suggestions surfaced in API/UI | feature/phase2-menu-insights | Completed | Medium | Anoushka | 2026-04-20 | 2026-04-20 | 2026-04-20 | 100% | P1-12 | Menu service, node, graph, and e2e tests passed | Merged to dev, branch deleted
Phase 2 | 22 | P2-04 | Frontend | Dashboard enhancement | Product-grade dashboard with stronger layout hierarchy, dedicated agent panels, top summary KPIs, clearer operational sections, and drill-down-ready UI | feature/phase2-dashboard-enhancement | Completed | High | Anoushka | 2026-04-21 | 2026-04-22 | 2026-04-26 | 100% | P2-02, P2-03 | Frontend checks + UI walkthrough + dashboard smoke tests | Merged to dev, branch deleted , (force-with-lease)
Phase 2 | 23 | P2-05 | Quality | Evaluation refinement | Manual rubric + scenario checklist + automated sanity checks (schema validation, quantity realism, 24h feasibility) + critic calibration notes | feature/phase2-evaluation-refinement | Completed | High | Anoushka | 2026-04-26 | 2026-04-26 | 2026-04-26 | 100% | P2-01, P2-02, P2-03, P2-04 | Eval checks + scenario validation + rubric doc | Merged to dev, branch deleted
Phase 2 | 24 | P2-06 | Release | Sync Phase 2 to main | Phase 2 milestone verified on main (forecast + inventory + menu + dashboard + evaluation); release verification + notes | dev -> main PR | Completed | Medium | Anoushka | 2026-04-26 | 2026-04-26 | 2026-04-26 | 100% | P2-05 | Milestone verification checklist | Main synced
Phase 3
Phase 3 | 25 | P3-01 | Product | Runs & audit UI | Run history persisted in Postgres; runs list + drilldown page showing agent outputs, critic score, rag context, trace/audit ids | feature/phase3-runs-audit-ui | Completed | Medium | Anoushka | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | P2-06 | API contract tests + UI smoke tests + trace retrieval tests | Merged to dev, branch deleted
Phase 3 | 26 | P3-02 | Quality | Advanced critic | Richer scoring dimensions + clearer revision reasons + actionable critic feedback for weak recommendations | feature/phase3-advanced-critic | Completed | Medium | Anoushka | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | P3-01 | Critic tests + scenario review + regression checks | Merged to dev, branch deleted
Phase 3 | 27 | P3-03 | Scoring | Cost-aware scoring | Recommendation scoring with operational cost/benefit awareness (prep burden, stock risk, feasibility tradeoffs) | feature/phase3-cost-aware-scoring | Completed | Medium | Anoushka | 2026-04-27 | 2026-04-27 | 2026-04-27 | 100% | P3-02 | Rule tests + scoring checks + e2e scenario tests | Merged to dev, branch deleted
Phase 3 | 28 | P3-04 | Product | Scenario expansion | Extend beyond Friday Rush (weekday/weekend, holiday spike, low-stock weekend); reusable workflow framing + UI selection | feature/phase3-scenario-expansion | Completed | Medium | Anoushka | 2026-04-28 | 2026-04-29 | 2026-04-29 | 100% | P3-03 | Scenario tests + e2e flow tests + UI smoke tests | Merged to dev, branch deleted
Phase 3 | 29 | P3-05 | Release | Sync Phase 3 to main | Advanced milestone stabilized on main | dev -> main PR | Completed | Low | Anoushka | 2026-04-29 | 2026-04-29 | 2026-04-29 | 100% | P3-04 | Milestone verification checklist + demo run checklist | Main synced
Demo prep
Demo prep | 30 | PD-01 | Data | Seed data | Additional Seed Data for demo and minor ui polish | chore/seed-data | Completed | Low | Anoushka | 2026-05-16 | 2026-05-16 | 2026-05-16 | 100% | NONE | Seeded Data successfully | Merged to dev, branch deleted
Demo prep | 31 | PD-02 | Frontend | minor ui polish | minor ui polish | feat/demo-prep | Completed | Low | Anoushka | 2026-05-16 | 2026-05-16 | 2026-05-16 | 100% | NONE | Ui polish pass | Merged to dev, branch deleted
Demo prep | 31 | PD-03 | Frontend | loading state improvements | minor ui polish | feat/quick-fix | Completed | Low | Anoushka | 2026-05-19 | 2026-05-19 | 2026-05-19 | 100% | NONE | Ui polish pass | Merged to dev, branch deleted
Phase 4
Phase 4 | 1 | P4-01 | Product | Multi-tenant + auth | Users/orgs, login, workspace separation, role-based access, protected pages | feature/phase4-auth-multitenant | Completed | High | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P3-05 | Auth tests + access-control tests + UI smoke tests | Merged to dev, branch deleted
Phase 4 | 2 | P4-02 | Observability | LangSmith tracing | Enable LangSmith trace capture for all LangGraph nodes — set LANGCHAIN_TRACING_V2 + API key; verify per-node traces visible in LangSmith UI | feature/phase4-langsmith-tracing | Completed | High | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P3-05 | Trace visibility smoke test — confirm node names, LLM calls, latency appear in LangSmith dashboard | Merged to dev, branch deleted
Phase 4 | 3 | P4-03 | Infra | Real dependency health checks | Replace stub URL-existence checks in dependency_health.py with actual pings: psycopg2.connect(), QdrantClient.get_collections(), redis.ping(); return latency_ms and error detail per dependency | feature/phase4-health-checks | Completed | High | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P3-05 | Health check integration tests — confirm each service returns ok=True when running, ok=False when stopped | Merged to dev, branch deleted
Phase 4 | 4 | P4-04 | Observability | Structured logging (structlog) | Replace default FastAPI logging with structlog JSON output: run_id, node, duration_ms on every event; add request middleware for HTTP access logs | feature/phase4-structlog | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-02 | Log output unit tests — verify JSON fields present; smoke test that run_id propagates through nodes | Merged to dev, branch deleted
Phase 4 | 5 | P4-05 | Observability | Node latency + LLM cost tracking | Record started_at/ended_at/duration_ms per node in execution_trace (always-on, not debug-only); add prompt_tokens, completion_tokens, cost_usd per LLM call using Gemini usage API; store in planning_runs.meta (jsonb) | feature/phase4-cost-latency | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-04 | Cost tracking unit tests — verify token fields populated; integration test checks meta column written after run | Merged to dev, branch deleted
Phase 4 | 6 | P4-06 | Product | Admin + settings | Scenario templates, thresholds, capacity, menu/inventory settings, tenant config UI | feature/phase4-admin-settings | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-01 | UI smoke tests + settings persistence tests | Merged to dev, branch deleted
Phase 4 | 7 | P4-07 | Product | Runs UI — filter + diff view | Add scenario filter, date range picker, and critic score trend chart to /runs page; add side-by-side diff modal comparing critic dimension scores between two selected runs | feature/phase4-runs-diff-ui | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-01 | Frontend smoke tests + API filter parameter tests | Merged to dev, branch deleted
Phase 4 | 8 | P4-08 | Product | Configurable restaurant profiles | Add restaurant_profiles table (name, cuisine, capacity, peak_hours, timezone); planning run accepts restaurant_id; scenarios pull context from profile instead of hardcoded pizza assumptions; one Alembic migration | feature/phase4-restaurant-profiles | Completed | Medium | Anoushka | 2026-05-31 | 2026-05-31 | 2026-05-31 | 100% | P4-06 | Migration smoke test + service unit tests + scenario context injection tests | Merged to dev, branch deleted
Phase 4 | 9 | P4-09 | Infra | LLM provider hot-swap + fallback | LLM_PROVIDER env var selects active provider (gemini¦groq); if primary fails mid-run, automatically retry with fallback provider; log provider used per run in structlog and LangSmith metadata | feature/phase4-llm-providers | Completed | Low | Anoushka | 2026-06-01 | 2026-06-01 | 2026-06-01 | 100% | P4-02 | Provider unit tests — verify complete() and complete_json() work for new providers; integration test with one full planning run per provider | Merged to dev, branch deleted
Phase 4 | 10 | P4-10 | Quality | RAGAS eval for complaint RAG pipeline | Integrate ragas to evaluate complaint_intelligence node: faithfulness, answer relevancy, context precision/recall scored against Qdrant retrieval; run as part of eval suite with LangSmith dataset | feature/phase4-ragas-evals | Completed | Low | Anoushka | 2026-06-01 | 2026-06-01 | 2026-06-01 | 100% | P4-02 | RAGAS metric thresholds pass (faithfulness > 0.8); eval script runs without error in CI | Merged to dev, branch deleted
Phase 4 | 11 | P4-11 | Quality | DeepEval LLM output quality tests | Add deepeval metrics to pytest suite: HallucinationMetric on critic output, AnswerRelevancyMetric on agent recommendations; gate CI — fail if quality drops below threshold | feature/phase4-deepeval | Completed | Low | Anoushka | 2026-06-03 | 2026-06-03 | 2026-06-03 | 100% | P4-10 | DeepEval tests pass in pytest; CI pipeline fails on hallucination score above threshold | Merged to dev, branch deleted
Phase 4 | 12 | P4-12 | Infra | MCP server — expose planning API | Wrap POST /planning/run and GET /runs as MCP tools using Anthropic Python MCP SDK; expose run_planning_scenario tool and get_run_history resource; test with Claude Desktop | feature/phase4-mcp-server | Completed | Low | Anoushka | 2026-06-03 | 2026-06-03 | 2026-06-03 | 100% | P4-01 | MCP tool smoke test — confirm Claude Desktop can trigger a planning run and retrieve run history | Merged to dev, branch deleted
Phase 4 | 13 | P4-13 | Release | Sync Phase 4 to main | Phase 4 milestone verified on main: auth, observability, evals, Redis cache, MCP server all stable. README updated. Demo run clean across all 4 scenarios. | dev -> main PR | Completed | Low | Anoushka | 2026-06-03 | 2026-06-03 | 2026-06-03 | 100% | P4-12 | Milestone verification checklist + demo run checklist + all Phase 4 integration tests green | Merged to main via dev PR
Phase 5
Phase 5 | 1 | P5-01 | Product | PDF export — manager summary | GET /runs/{id}/export?format=pdf — one-page summary with critic score, action items, forecast; WeasyPrint or reportlab; downloadable from runs page | feature/phase5-pdf-export | Completed | High | Anoushka |  |  |  | 0% | P4-13 | PDF generation unit test — all sections present; download endpoint smoke test | No blockers — quick win, strong demo artifact
Phase 5 | 2 | P5-02 | Product | Excel export — role-aware | GET /runs/{id}/export?format=xlsx — inventory + staffing sheet for chef, cost breakdown for owner; formatted with openpyxl; separate sheets per role | feature/phase5-excel-export | Completed | High | Anoushka |  |  |  | 0% | P5-01 | Excel generation unit test — verify sheets and headers; download endpoint smoke test | Pairs with P5-01
Phase 5 | 3 | P5-03 | Product | Frontend UX fixes | Fix /data-health 404 (page missing, NavBar links to it); add restaurant profile selector to dashboard run form; add export download buttons to runs page; add input validation to settings page; surface cost/token aggregate on runs list | feature/phase5-frontend-ux | Completed | High | Anoushka |  |  |  | 0% | P5-01 | Smoke tests: data-health loads; profile selector sends restaurant_id; settings rejects invalid range | Fixes live 404 bug. Frontend-only — no API changes needed
Phase 5 | 4 | P5-04 | Infra | Redis caching for planning runs | Cache planning run results by scenario+date key (TTL 1hr) using aioredis; skip full graph on cache hit; add cache_hit flag to response; Redis already in docker-compose | feature/phase5-redis-cache | Completed | Medium | Anoushka |  |  |  | 0% | P4-13 | Cache unit tests — hit/miss logic; integration test: second identical run returns faster with cache_hit=True | Redis already running — no infra change needed
Phase 5 | 5 | P5-05 | Infra | SSE streaming — node-by-node results | Stream planning run results node-by-node to frontend via Server-Sent Events; frontend renders each agent card as its node completes; reduces perceived latency significantly | feature/phase5-streaming | Completed | Medium | Anoushka |  |  |  | 0% | P5-04 | SSE endpoint smoke test — events emitted per node; frontend confirms cards render progressively | No async queue needed — SSE works on sync runs
Phase 5 | 6 | P5-06 | Product | What-if simulator | Sliders for covers/date/scenario in UI — re-run only forecast + cost nodes via partial LangGraph execution — instant updated output without full planning run | feature/phase5-whatif-simulator | Completed | Medium | Anoushka |  |  |  | 0% | P4-08 | Partial graph execution unit test; UI slider integration test; output diff from full run test | No blockers — works with synthetic data, strong interactive demo
Phase 5 | 7 | P5-07 | Observability | OpenTelemetry + Prometheus metrics | Add opentelemetry-instrumentation-fastapi + prometheus-fastapi-instrumentator; expose /metrics endpoint; capture HTTP request latency, throughput, error rate; Grafana dashboard | feature/phase5-opentelemetry | Completed | Medium | Anoushka |  |  |  | 0% | P4-05 | Prometheus scrape test — /metrics returns valid prom format; Grafana panels show data | Pure infra — no data dependency
Phase 5 | 8 | P5-08 | Infra | Sentry error tracking | Add sentry-sdk[fastapi]; capture unhandled exceptions, slow transactions, LangGraph node errors; verify error appears in Sentry on intentional 500 | feature/phase5-sentry | Completed | Low | Anoushka |  |  |  | 0% | P4-05 | Sentry capture smoke test — intentional exception appears within 30s | Quick win — ~1 day effort
Phase 5 | 9 | P5-09 | Quality | LangSmith dataset + regression evals | Build golden dataset from best historical planning runs already in DB; run automated evaluators (critic score > 3.5, plan contains restock recommendation); fail CI on regression | feature/phase5-langsmith-evals | Completed | Medium | Anoushka |  |  |  | 0% | P4-02 | Eval pass rate > 90% on golden dataset; CI fails on intentional prompt regression | We already have runs in the DB — use those as golden dataset
Phase 5 | 10 | P5-10 | Product | Multi-tenant workspace isolation | Full tenant isolation: Postgres row-level security per org; Qdrant shared collection with restaurant_id + doc_type payload filters (NOT per-tenant collections — see D-009); no data bleed between orgs | feature/phase5-tenant-isolation | Completed | High | Anoushka |  |  |  | 0% | P4-01 | Tenant isolation tests — verify org A cannot read org B runs; Qdrant filter tests | Auth done in P4-01. Qdrant: payload pre-filter only, not per-tenant collections
Phase 5 | 11 | P5-11 | Product | Weekly digest email | Auto-generated Sunday summary + Monday recommendations via APScheduler; formatted email via SendGrid/Resend; per-restaurant scheduling; PDF attached | feature/phase5-weekly-digest | Completed | Medium | Anoushka |  |  |  | 0% | P5-01 | Scheduler unit test; email template render test; send smoke test with test API key | Works with synthetic data — auth and PDF export must be done first
Phase 5 | 12 | P5-12 | Product | RAG chatbot over run history | Conversational interface: answer questions like why did critic score drop last Friday — retrieves relevant runs + complaints from Postgres + Qdrant, streams reply via SSE; multi-turn memory | feature/phase5-rag-chatbot | Completed | High | Anoushka |  |  |  | 0% | P5-05 | Retrieval unit test; multi-turn memory test; SSE streaming smoke test; hallucination check via DeepEval | SSE must be done first (P5-05). Works with synthetic run history
Phase 5 | 13 | P5-13 | Release | Sync Phase 5 to main | Phase 5 milestone verified: PDF/Excel export, SSE streaming, Redis cache, tenant isolation all stable. README and docs updated. | dev -> main PR | Completed | Low | Anoushka |  |  |  | 0% | P5-12 | Milestone checklist + demo run with all Phase 5 features active | Update docs after merge
Phase 6
Phase 6 | 0 | P6-00 | Infra | Per-node model tier routing via CometAPI | CometProvider (AsyncOpenAI), 3-tier registry (fast/balanced/strong), llm_registry in OrchestratorState, node-level tier overrides, cost tracking across all tiers. LangSmith verified per-node model assignment. Async fix cut fan-out from 48.7s to 17s. | feature/per-node-model-routing | Completed | High | anoushka | 2026-06-19 | 2026-06-19 | 2026-06-19 | 100% |  | No | Merged to dev 2026-06-19. PR: feat: per-node model tier routing via CometAPI
Phase 6 | 0 | P6-00b | Agents | Cross-agent assumption diffing | Each domain node writes assumptions dict to OrchestratorState after its service call. EvaluationSanityChecker._diff_assumptions() cross-diffs them post fan-out (4 checks: stockout, capacity, forecast confidence, complaint gray zone). stale_assumptions injected into critic LLM prompt and returned in critic.stale_assumptions in API response. final_assembler bug fix included. 9 docs updated. | feature/assumption-diffing | Completed | High | Anoushka | 2026-06-26 | 2026-06-26 | 2026-06-26 | 100% | P6-00 | Unit tests: existing EvaluationSanityChecker tests still pass; stale_assumptions in check_bundle output | Merged to dev, branch deleted
Phase 6 | 0 | P6-00c | Agents | Drop Diff 1, v3 reseed, stale_assumptions fix | Dropped false-positive Diff 1. v3 seed data. stale_assumptions passthrough fixed. | feature/drop-diff1-reseed-data | Completed | High | Anoushka | 2026-06-26 | 2026-06-26 | 2026-06-26 | 100% | P6-00b | Existing diffs pass; API returns stale_assumptions | Merged to dev
Phase 6 | 1 | P6-S01 | Integrations | BaseConnector + SwiggyMCPClient | BaseConnector ABC (sync/enrich), SwiggyMCPClient (JSON-RPC 2.0, httpx, graceful degradation — never raises), SwiggyConnector skeleton, enrichers/ + executor/ package stubs, CLAUDE.md at root, swiggy_access_token + swiggy_address_id in settings | feature/swiggy-base-connector | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-27 | 2026-06-27 | 1 | P6-00c | 7 tests: is_available True/False; call_tool returns None on 401, 500 (x2 retry verified), success data dict, never raises on Exception, returns None on success=false | Merged to dev 2026-06-27. PR #80. CLAUDE.md created. Migration verified live on DB.
Phase 6 | 2 | P6-S02 | Infra | connectors table + async job queue | Alembic migration b3e1f2a9c5d7: connectors table (11 cols, uq org+type), orders.source/channel/external_order_id, reservations.source/external_booking_id, feedback delivery timing cols, swiggy_delivery enum value. ConnectorRepository (upsert, token, sync status). Redis async job queue (24h TTL, uuid4 IDs, no external library). | feature/swiggy-base-connector | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-27 | 2026-06-27 | 1 | P6-S01 | 6 tests: upsert creates, upsert idempotent (1 row), get returns None, error_count increments, error clears on success, list_active filter. Migration smoke: alembic upgrade head + psycopg2 verify all cols + enum. | Merged to dev 2026-06-27. PR #80. Migration verified live on Docker Postgres.
Phase 6 | 3 | P6-S03 | Integrations | SwiggyOrderSyncService — get_food_orders → orders table | SwiggyOrderSyncService.sync(address_id): fetches up to 20 Swiggy delivery orders, creates one Order row per item (source=swiggy, channel=delivery, is_delivery=True, external_order_id={orderId}_{idx}). _get_or_create_menu_item: case-insensitive name match; placeholder (is_available=False) if no match. Idempotent. SwiggyConnector.sync() implemented: reads SWIGGY_ADDRESS_ID, sets connector status syncing→success/error. BaseConnector updated: db: Session added to __init__. | feature/swiggy-sync-orders | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-27 | 2026-06-27 | 1 | P6-S02 | 8/8 pass: correct count, Order fields, placeholder MenuItem, reuse existing MenuItem, idempotency, None graceful, empty list, ext_id format | Merged to dev 2026-06-27. Mock-first (no Swiggy token needed). Live integration test pending token.
Phase 6 | 4 | P6-S04 | Agents + Infra | Agent Intelligence Bundle | Aggregator contradiction detection (0 LLM calls). Critic replanning loop max 2 retries. Qdrant early enrichment layer. Semantic cache (planning + chatbot, Qdrant, threshold 0.92). Chatbot tool use via Groq function calling. Cross-session memory in Qdrant. Proactive pattern surfacing on session start. | feature/agent-intelligence | In Progress | Critical | Anoushka | 2026-06-27 | 2026-06-28 |  | 0 | P6-S03 | Contradiction fires; replanning routes correctly; cache hit; chatbot tools return data; cross-session memory persists | Building now (2026-06-27). Mock-first where needed. No Swiggy token required.

## Phase 6
CortexKitchen — Phase 6: Unified Roadmap (Swiggy Integration + Original P6 Tasks)
Week | Task ID | Feature Branch | Workstream | Task | Detailed Outcome / Done Means | PR Description Hook | Docs Updated | Status | Priority | Owner | Start | Target | % Done | Depends On | Tests Expected
ALREADY DONE — P6-00 series (merged to dev)
— | P6-00 | feature/per-node-model-routing | Infra | Per-node model tier routing via CometAPI | CometProvider (AsyncOpenAI), 3-tier registry (fast/balanced/strong), llm_registry in OrchestratorState, node-level tier overrides, cost tracking. Fan-out latency: 48.7s → 17s. | feat: per-node model tier routing via CometAPI | docs/ARCHITECTURE.md, docs/DECISIONS.md | Completed | High | Anoushka | 2026-06-19 | 2026-06-19 | 100% | P5-13 | LangSmith traces show per-node model; cost_usd tracked per tier
— | P6-00b | feature/assumption-diffing | Agents | Cross-agent assumption diffing | 4 domain nodes write assumptions dicts. EvaluationSanityChecker._diff_assumptions() runs 3 cross-diffs post fan-out. stale_assumptions injected into critic prompt + returned in API. final_assembler bug fix. 9 docs updated. | feat: cross-agent assumption diffing — O(N²) → O(N) | 9 docs updated | Completed | High | Anoushka | 2026-06-26 | 2026-06-26 | 100% | P6-00 | Existing sanity checker tests pass; stale_assumptions in API response
— | P6-00c | feature/drop-diff1-reseed-data | Agents | Drop Diff 1, v3 reseed, stale_assumptions API fix | Diff 1 removed (MenuService self-queries inventory — parallel execution means diff fires as false positive). v3 seed data. stale_assumptions passthrough fixed in final_assembler. | fix: drop Diff 1 false positive, v3 reseed, stale_assumptions API fix | docs/AGENTS.md | Completed | High | Anoushka | 2026-06-26 | 2026-06-26 | 100% | P6-00b | 3 remaining diffs fire correctly; API response carries stale_assumptions
WEEK 1 — Foundation: Connector Layer + Async Jobs
W1 | P6-S01 | feature/swiggy-base-connector | Integrations | BaseConnector + SwiggyMCPClient | Abstract BaseConnector ABC with sync() and enrich() methods. SwiggyMCPClient: per-org OAuth token (5-day TTL, re-auth on 401, encrypted storage), JSON-RPC 2.0 calls to /food + /im + /dineout, exponential backoff retry, is_available() check, structured logging. Absorbs original P6-01. | feat: connector layer — BaseConnector ABC + SwiggyMCPClient with per-org OAuth | docs/ARCHITECTURE.md (connector layer section), docs/DECISIONS.md (D-019), docs/DATA_MODEL.md, CLAUDE.md (new), docs/SWIGGY_INTEGRATION.md | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-27 | 100% | P6-00c | 13/13 pass — test_swiggy_client.py (7): is_available, 401 no-retry, 500 retry x2, success data, never raises, success=false; test_connector_repository.py (6): upsert create, upsert idempotent, get none, error_count increment, error clear on success, list_active filter
W1 | P6-S02 | feature/swiggy-base-connector | Infra | connectors table + async job queue | Alembic migration: connectors table (org_id, connector_type, access_token_encrypted, token_expires_at, last_sync_at, sync_status, error_count). Redis job queue for async planning runs (absorbs original P6-02): job_id, status endpoint, dedup by scenario+date, non-blocking HTTP. | feat: connectors table + async Redis job queue for planning runs | docs/DATA_MODEL.md (connectors table, orders/reservations/feedback new cols), docs/ARCHITECTURE.md, docs/DECISIONS.md (D-019) | Completed | Critical | Anoushka | 2026-06-27 | 2026-06-27 | 100% | P6-S01 | Migration smoke test (alembic upgrade head verified live on DB); connectors table + all new cols confirmed via psycopg2; swiggy_delivery enum value present
WEEK 2 — Real Data Sync: Orders, Reservations, Feedback
W2 | P6-S03 | feature/swiggy-sync-orders | Integrations | Sync Swiggy orders → orders table | Nightly sync job: get_food_orders (last 15 days) → orders table with source='swiggy', channel='delivery'. Dedup by external_order_id. Upsert. ForecastService gains channel filter so Prophet trains on delivery demand separately from dine-in. Absorbs original P6-03 for delivery channel. | feat: swiggy order sync — get_food_orders nightly → orders table (source=swiggy, channel=delivery) | docs/SWIGGY_INTEGRATION.md (P6-S03 ✅, status header updated) | Completed | High | Anoushka | 2026-06-27 | 2026-06-27 | 100% | P6-S02 | 8/8 pass — correct count, correct Order fields (source/channel/is_delivery), placeholder MenuItem creation (is_available=False, category=swiggy_import), reuse existing MenuItem by name, idempotency on duplicate sync, None call_tool graceful, empty order list, external_order_id format SW-001_0/SW-001_1
W2 | P6-S04 | feature/agent-intelligence | Agents + Infra | Agent Intelligence Bundle — smarter pipeline + agentic chatbot | Aggregator contradiction detection (pure Python, 0 LLM calls): detects demand_forecast vs inventory conflicts, appends DETECTED CONTRADICTIONS to critic summary. Critic replanning loop: rejected/revision → replan_orchestrator injects critic notes → aggregator re-runs → critic re-evaluates, max 2 retries (+1 LLM call/retry). Qdrant early enrichment: 1 shared retrieval step before parallel nodes, all agents get pre-loaded context. Semantic cache: Qdrant embedding-based lookup (threshold 0.92) for planning runs + chatbot queries. Chatbot tool use: Groq function calling — query_runs, get_run_detail, trigger_planning_run, get_inventory_status. Cross-session memory: Qdrant session summaries per user. Proactive pattern surfacing: chatbot detects recurring critic failures on session start. | feat: agent intelligence — contradiction detection, replanning loop, semantic cache, agentic chatbot | docs/ARCHITECTURE.md (replanning loop, Qdrant enrichment), docs/AGENTS.md (aggregator update) | In Progress | Critical | Anoushka | 2026-06-27 | 2026-06-28 | 0 | P6-S03 | Contradiction detection: demand_forecast vs inventory conflict fires correctly. Replanning: rejected plan routes back, critic re-evaluates with notes. Semantic cache: cache hit returns plan without LLM call. Chatbot tools: query_runs returns structured data; trigger_planning_run starts a run. Cross-session memory: session summary persists in Qdrant, retrieved on next session.
W2 | P6-S05 | Waiting: Swiggy token pending | Integrations | Sync Dineout bookings → reservations table | get_booking_status for all active Dineout bookings → reservations table with source='dineout'. Track confirmed/no-show/cancelled. ReservationService gains source filter. Absorbs original P6-04 for Dineout channel (Resy/OpenTable deferred to P6-R02). | feat: dineout reservation sync — get_booking_status → reservations table (source=dineout) | docs/DATA_SOURCES.md (Dineout reservations), docs/DATA_MODEL.md | Blocked | High | Anoushka |  | W2 | 0% | P6-S02 | Sync idempotency; source filter on ReservationService; booking status mapping test
W2 | P6-S06 | Waiting: Swiggy token pending | Integrations | Sync delivery performance → feedback table | track_food_order → feedback rows: source='swiggy_delivery', prep_time_actual, delivery_time_actual, promised_time, late_flag. ComplaintService surfaces delivery latency patterns. RAG runs over real delivery feedback in Qdrant. | feat: swiggy delivery signal sync — track_food_order → feedback table (source=swiggy_delivery) | docs/DATA_SOURCES.md (delivery feedback), docs/AGENTS.md (complaint_intel updated) | Blocked | High | Anoushka |  | W2 | 0% | P6-S03 | Latency mapping test; late_flag logic; ComplaintService source filter; RAG retrieval returns real delivery complaints
WEEK 3 — Market Intelligence: Live Enrichment
W3 | P6-S07 | feature/swiggy-market-intel-enrichers | Agents | CompetitorEnricher — Food MCP | search_restaurants (cuisine, addressId) → filter OPEN → search_menu + get_restaurant_menu per restaurant (max 3) → competitor_pricing dict: area avg price per dish category, pricing alerts vs your menu. Redis cache 30min TTL. Supersedes original P6-07 (no scraping needed). | feat: CompetitorEnricher — live competitor pricing via Food MCP | docs/SWIGGY_INTEGRATION.md (new, CompetitorEnricher section), docs/AGENTS.md (menu_intel updated) | Planned | High | Anoushka |  | W3 | 0% | P6-S02 | Structured dict with area_avg_price; graceful None on failure; Redis cache hit; menu_intel prompt includes market context
W3 | P6-S08 | feature/swiggy-market-intel-enrichers | Agents | OccupancyEnricher — Dineout MCP | get_saved_locations → search_restaurants_dineout → get_restaurant_details (top 3) → get_available_slots (today) → occupancy_signal: HIGH/MEDIUM/LOW, tonight_busy bool. Redis cache 30min TTL. Supersedes original P6-06 Google Trends approach. | feat: OccupancyEnricher — live competitor occupancy via Dineout MCP | docs/SWIGGY_INTEGRATION.md (OccupancyEnricher section), docs/AGENTS.md (reservation updated) | Planned | High | Anoushka |  | W3 | 0% | P6-S07 | HIGH/MEDIUM/LOW logic test; graceful None; reservation node prompt includes occupancy
W3 | P6-S09 | feature/swiggy-procurement-l1 | Agents | ProcurementEnricher — Instamart (read-only) | For each shortage_alert item: search_products (addressId, ingredient) → spinId, price, unit, availability. Also your_go_to_items for frequent reorder suggestions. procurement_options dict injected into inventory node prompt. spinId stored for later execution. | feat: ProcurementEnricher — live Instamart ingredient pricing injected into inventory node | docs/SWIGGY_INTEGRATION.md (ProcurementEnricher section), docs/AGENTS.md (inventory updated) | Planned | High | Anoushka |  | W3 | 0% | P6-S07 | procurement_options per shortage item; spinId captured; graceful None; inventory prompt includes live prices
W3 | P6-S10 | feature/swiggy-market-intel-enrichers | Infra | MarketIntelService + 6 new OrchestratorState fields | MarketIntelService orchestrates all 3 enrichers. Adds 6 Annotated[Optional[Dict], keep_last] fields to OrchestratorState: swiggy_competitor_context, swiggy_occupancy_context, swiggy_procurement_options, swiggy_delivery_signal, market_intel_output, dineout_manager_output. | feat: MarketIntelService + 6 new OrchestratorState enrichment fields | docs/ARCHITECTURE.md (MarketIntelService), docs/DATA_MODEL.md (state fields) | Planned | High | Anoushka |  | W3 | 0% | P6-S07 | State field type tests; MarketIntelService runs all 3 enrichers; final_assembler passes through
WEEK 4 — New Nodes: Pipeline Expands to 11 Nodes
W4 | P6-S11 | feature/swiggy-market-intel-node | Agents | market_intel_node — 10th LangGraph node | New parallel domain node. Runs CompetitorEnricher + OccupancyEnricher. Outputs market_intel_output: competitor_pricing, area_occupancy, pricing_alerts. Writes market_assumptions dict. Participates in assumption diffing. Critic receives market context. Supersedes original P6-06. | feat: market_intel_node — 10th parallel LangGraph node, Swiggy-powered market awareness | docs/AGENTS.md (market_intel_node section), docs/ARCHITECTURE.md (11-node pipeline), docs/DECISIONS.md (D-020) | Planned | High | Anoushka |  | W4 | 0% | P6-S10 | Node writes market_intel_output + market_assumptions; parallel verified; assumption diffing fires; LangSmith trace shows node
W4 | P6-S12 | feature/swiggy-dineout-manager-node | Agents | dineout_manager_node — 11th LangGraph node | New parallel domain node. get_booking_status checks your own Dineout booking density. get_available_slots checks remaining capacity. If reservation node predicts high walk-in AND slots low → queues book_table action. Writes dineout_assumptions dict. | feat: dineout_manager_node — 11th parallel LangGraph node, manages your Dineout presence | docs/AGENTS.md (dineout_manager_node section), docs/ARCHITECTURE.md | Planned | High | Anoushka |  | W4 | 0% | P6-S11 | Writes dineout_manager_output + dineout_assumptions; book_table action queued when conditions met; LangSmith trace
W4 | P6-S13 | feature/swiggy-market-intel-node | Agents | Assumption diffs 5 + 6 for new nodes | Diff 5: market_intel assumed_competitor_avg_price vs menu_intel items_assumed_available pricing. Diff 6: dineout_manager assumed_dineout_slots_low vs reservation assumed_peak_occupancy. Extends P6-00b. Total now 5 active diffs. | feat: assumption diffs 5+6 — market vs menu pricing, dineout slots vs reservation occupancy | docs/ARCHITECTURE.md (sanity checker updated), docs/AGENTS.md | Planned | Medium | Anoushka |  | W4 | 0% | P6-S11 | Diff 5 + 6 fire correctly; existing 3 diffs unaffected; stale_assumptions includes new conflicts
WEEK 5 — Action Layer: Execution + Approval Gates
W5 | P6-S14 | feature/swiggy-action-queue | Product | ActionQueueService + action_queue table | New table: id, org_id, action_type (AUTO/APPROVE_REQUIRED/RECOMMENDATION), payload jsonb, status (PENDING/APPROVED/EXECUTED/REJECTED/EXPIRED), approved_by, executed_at, error. ActionQueueService CRUD. Plan output includes action_queue section in API response. | feat: ActionQueueService + action_queue table — 3-tier action model with approval lifecycle | docs/ACTION_QUEUE.md (new), docs/APIS.md (action queue endpoints), docs/DECISIONS.md (D-021) | Planned | High | Anoushka |  | W5 | 0% | P6-S10 | Action CRUD tests; status transitions PENDING→APPROVED→EXECUTED; plan response includes action_queue; expired cleanup
W5 | P6-S15 | feature/swiggy-procurement-l2 | Agents | ProcurementExecutor — Instamart checkout (ReAct pattern) | ReAct-style execution (absorbs original P6-05): LLM observes search_products result, refines query if needed (max 3 iterations), selects variant. Then: get_cart → clear_cart → update_cart (spinIds) → get_cart → LangGraph interrupt() → owner approval → checkout. Check-then-retry on 5xx. procurement_orders table. | feat: ProcurementExecutor — ReAct ingredient search + Instamart checkout with approval gate | docs/ACTION_QUEUE.md (procurement flow), docs/SWIGGY_INTEGRATION.md (checkout non-idempotency) | Planned | High | Anoushka |  | W5 | 0% | P6-S14 | ReAct max 3 iterations; check-then-retry on 5xx; interrupt() pauses graph; approval resumes checkout; procurement_orders row created
W5 | P6-S16 | feature/swiggy-action-queue | Agents | Dineout table booking execution | When dineout_manager_node queues book_table and owner approves: create_cart (DEAL_TICKET_PURCHASE) → book_table (slotId, itemId, reservationTime, guestCount, lat/lng). On 5xx: get_booking_status before retry. Confirmation written to reservations table. | feat: Dineout table booking execution with approval gate | docs/SWIGGY_INTEGRATION.md (book_table non-idempotency), docs/ACTION_QUEUE.md | Planned | Medium | Anoushka |  | W5 | 0% | P6-S14 | Non-idempotent retry test; end-to-end approval flow; confirmation in reservations table; rejection has no side effects
WEEK 6 — Product Modes: Brief, Live, MCP Expansion
W6 | P6-S17 | feature/swiggy-brief-mode | Product | BriefingService — automated 7am daily brief | APScheduler job at 07:00 IST per org. Lightweight run: demand_forecast + market_intel_node only. Pulls overnight Swiggy signals (get_food_orders since last run, track_food_order performance). Generates daily_brief JSON. Stores in daily_briefs table. Email digest (extends P5-11). | feat: BriefingService — automated daily morning brief with overnight Swiggy signals | docs/PRODUCT_MODES.md (new, brief mode), docs/APIS.md (brief endpoints) | Planned | Medium | Anoushka |  | W6 | 0% | P6-S10 | Scheduler fires at correct time; brief generates without full pipeline; daily_briefs row created; email sends
W6 | P6-S18 | feature/swiggy-live-mode | Product | LiveMonitorService — real-time during service hours | SSE feed during service hours (12:00-14:00, 19:00-22:00 IST). Polls every 30s: get_food_orders (active), track_food_order (in-flight), track_order (Instamart procurement). Alerts: delivery > threshold, order spike, ingredient arrived. Stops outside service window. | feat: LiveMonitorService — real-time SSE ops monitor during service hours | docs/PRODUCT_MODES.md (live mode section), docs/APIS.md (live SSE endpoint) | Planned | Medium | Anoushka |  | W6 | 0% | P6-S15 | SSE events fire; 30s poll verified; alerts trigger correctly; stops outside service hours
W6 | P6-S19 | feature/swiggy-mcp-tools | Infra | 3 new CortexKitchen MCP server tools | Add to mcp_server.py: get_market_brief (calls MarketIntelService live, returns competitor snapshot for Claude Desktop), get_action_queue (pending actions awaiting approval), approve_action (owner approves from Claude Desktop, triggers execution). JWT auth on all 3. | feat: 3 new MCP tools — get_market_brief, get_action_queue, approve_action | docs/APIS.md (MCP tools section), docs/ARCHITECTURE.md (MCP server updated) | Planned | Medium | Anoushka |  | W6 | 0% | P6-S14 | All 3 tools smoke-tested in Claude Desktop; approve_action triggers execution end-to-end; JWT enforced
WEEK 6-7 — Original P6 Tasks (POS Connector + Voice)
W6 | P6-R01 | feature/swiggy-pos-connector | Integrations | POS connector — Square/Toast CSV (2nd connector) | Second implementation of BaseConnector. CSV import from Square/Toast export. Maps dine-in orders to orders table with source='pos', channel='dine_in'. Dedup by external_order_id. Validates against InventoryService and ForecastService. Now ForecastService has both delivery (Swiggy) and dine-in (POS) channels. | feat: POSConnector — Square/Toast CSV import, source=pos, channel=dine_in | docs/CONNECTORS.md (POSConnector section), docs/DATA_SOURCES.md (POS section) | Planned | Medium | Anoushka |  | W6 | 0% | P6-S03 | CSV import unit tests; ForecastService integration with both channels; dedup test; InventoryService validation
W7 | P6-R02 | feature/swiggy-voice-interface | Product | Voice interface — Whisper + RAG chatbot | Whisper transcription on browser-recorded question (MediaRecorder API). RAG chatbot (P5-12) answers. TTS reads back. Manager asks questions while walking the floor. Works with both synthetic and real Swiggy data now in DB. Blocked on P5-12 (already done). | feat: voice interface — Whisper transcription + RAG answer + TTS readback | docs/PRODUCT_MODES.md (voice section) | Planned | Low | Anoushka |  | W7 | 0% | P6-S16 | Transcription accuracy smoke test; end-to-end voice → RAG answer → TTS; works with real Swiggy data in DB
WEEK 7 — Frontend: 5 New Pages + 3 New Panels
W7 | P6-F01 | feature/swiggy-frontend-market | Frontend | Market intelligence panel (planning results page) | New panel on /runs/{id}. Competitor pricing table: your price vs area avg vs cheapest competitor per dish category. Area occupancy badge (HIGH/MEDIUM/LOW). Instamart prices for shortage items. Pricing alerts (red if >20% above area avg). Hidden when market_intel_output absent. | feat: market intelligence panel — competitor pricing + area occupancy on planning results | None (frontend only) | Planned | High | Anoushka |  | W7 | 0% | P6-S10 | Panel renders when data present; hides gracefully when not; pricing alerts correct; occupancy badge correct
W7 | P6-F02 | feature/swiggy-frontend-actions | Frontend | Action queue UI + procurement tracker | New section below plan output. Lists pending actions with type badge. Approve/Reject buttons for APPROVE_REQUIRED. Instamart cart preview modal (items, total, ETA) before approving checkout. Procurement tracker in inventory panel: placed orders, status, ETA. | feat: action queue UI — approve/reject with cart preview, procurement tracker | None (frontend only) | Planned | High | Anoushka |  | W7 | 0% | P6-S13 | Action list renders; approve triggers API; cart preview correct; reject has no side effects; tracker updates on delivery
W7 | P6-F03 | feature/swiggy-frontend-brief | Frontend | /brief page — daily morning briefing | New route /brief. Overnight Swiggy performance (orders, avg delivery time, late %), today's demand forecast vs yesterday, top 3 action priorities, market snapshot. Auto-refreshes if brief is stale. Empty state when no brief yet. | feat: /brief page — daily morning operational briefing | None (frontend only) | Planned | Medium | Anoushka |  | W7 | 0% | P6-S16 | Page loads; stale brief triggers refresh; all 4 sections render; empty state works
W7 | P6-F04 | feature/swiggy-frontend-connectors | Frontend | /connectors page — data source management | New route /connectors. Lists connectors with status badges (Connected/Disconnected/Error). Shows last sync time, records synced, data freshness. Connect button triggers OAuth flow. Disconnect revokes token. Error state shows last error + reconnect. Works for Swiggy + future POS connector. | feat: /connectors page — platform data source management with OAuth connect flow | None (frontend only) | Planned | Medium | Anoushka |  | W7 | 0% | P6-S01 | Connect triggers OAuth; post-OAuth shows Connected; Disconnect revokes; error state renders; POS connector appears as available
W7 | P6-F05 | feature/swiggy-frontend-live | Frontend | /live page — real-time ops monitor | New route /live. Active during service hours (countdown outside). SSE feed: active Swiggy orders + ETA, delivery performance gauge (green/amber/red), Instamart procurement in-flight status, alert feed (last 10). Auto-connects SSE on load. | feat: /live page — real-time service-hours ops monitor via SSE | None (frontend only) | Planned | Medium | Anoushka |  | W7 | 0% | P6-S17 | SSE connects; events update UI; countdown outside hours; gauge updates; alert feed shows last 10
W7 | P6-F06 | feature/swiggy-frontend-market | Frontend | Dashboard enhancements | Add to existing dashboard: connector status widget (data source health bar), brief mode trigger button, today's Swiggy KPIs (orders today, delivery rating, top Swiggy seller), data_sources column on /runs list. | feat: dashboard — connector status widget, brief trigger, live Swiggy KPIs, data_sources on runs list | None (frontend only) | Planned | Medium | Anoushka |  | W7 | 0% | P6-S16 | Connector widget shows status; brief trigger fires; Swiggy KPIs render; runs list data_sources column correct
WEEK 8 — Docs + Merge: Phase 6 Complete
W8 | P6-D01 | feature/swiggy-docs | Docs | 5 new documentation files | CONNECTORS.md: BaseConnector interface, sync vs enrich, how to add new connector. SWIGGY_INTEGRATION.md: all 22 tools, parameter mappings, OAuth, rate limits, error handling. ACTION_QUEUE.md: action types, approval flow, non-idempotent patterns. DATA_SOURCES.md: all sources, channels, sync frequency. PRODUCT_MODES.md: ops/brief/live/voice mode specs. | docs: 5 new documentation files for Phase 6 connector + action + product mode layer | docs/CONNECTORS.md, docs/SWIGGY_INTEGRATION.md, docs/ACTION_QUEUE.md, docs/DATA_SOURCES.md, docs/PRODUCT_MODES.md | Planned | High | Anoushka |  | W8 | 0% | P6-F06 | All 5 files present; no broken links; tool parameter tables accurate vs Swiggy docs
W8 | P6-D02 | feature/swiggy-docs | Docs | Update 8 existing docs | ARCHITECTURE.md: connector layer, 11-node pipeline, action layer, product modes. AGENTS.md: 2 new nodes + 2 new diffs. APIS.md: all new endpoints. DATA_MODEL.md: 6 new tables. DECISIONS.md: D-019 through D-022. ROADMAP.md: Phase 6 in-progress. EVALUATION.md: new node eval criteria. README.md: updated product headline. | docs: update 8 existing docs to reflect full Phase 6 additions | ARCHITECTURE, AGENTS, APIS, DATA_MODEL, DECISIONS, ROADMAP, EVALUATION, README | Planned | High | Anoushka |  | W8 | 0% | P6-D01 | No stale 9-node pipeline references; all new endpoints in APIS.md; D-019 through D-022 in DECISIONS.md
W8 | P6-D03 | dev -> main PR | Release | Phase 6 milestone merge to main | Merge feature/ck-v2-platform → dev → main. All 11 nodes verified in LangSmith. All 22 Swiggy tools exercised in staging. POS connector imports CSV end-to-end. Voice interface smoke tested. Action queue end-to-end. All 3 product modes verified. 5 new frontend pages smoke tested. Full test suite green. | release: Phase 6 complete — CortexKitchen v2 Swiggy-native restaurant OS | README.md (portfolio headline), docs/ROADMAP.md (Phase 6 complete) | Planned | Critical | Anoushka |  | W8 | 0% | P6-D02 | Full test suite green; 11 nodes in LangSmith; staging demo clean; portfolio README updated; docs website prep checklist done
PHASE 7 — Production, CI/CD, Docs Website
P7 | P7-01 | feature/phase7-cicd | Release | CI/CD — GitHub Actions | Automated on every PR: unit + integration + RAGAS evals + DeepEval; lint; type check; frontend build; coverage report. Fail on critic score regression. Cache pip dependencies. | feat: CI/CD — automated test + eval pipeline on every PR | docs/ROADMAP.md | Planned | High | Anoushka |  | P7 | 0% | P6-D03 | CI passes on clean repo; fails on intentional test break; eval regression detected
P7 | P7-02 | feature/phase7-cloud-deploy | Release | Cloud deployment — Railway / Fly.io | Containerise API + frontend. Deploy to Railway or Fly.io. Managed Postgres + Redis + Qdrant. Production env vars. Swiggy OAuth redirect URI updated for production domain. Health endpoint green on production URL. | feat: cloud deployment — production on Railway/Fly.io | docs/ROADMAP.md | Planned | High | Anoushka |  | P7 | 0% | P7-01 | Production URL health check green; all env vars; Swiggy OAuth works on production domain
P7 | P7-03 | feature/phase7-prod-hardening | Release | Production hardening | Rate limiting (slowapi). Secrets management (not env file). CORS lockdown. JWT key rotation. Sentry alerts tuned for production. Load test with k6. | feat: production hardening — rate limiting, secrets, CORS, JWT rotation | docs/ROADMAP.md | Planned | Medium | Anoushka |  | P7 | 0% | P7-02 | Rate limit smoke test; CORS rejection; Sentry alert fires on 500; k6 load test passes
P7 | P7-04 | feature/phase7-docs-website | Docs | Mintlify docs website | Point Mintlify at docs/ folder. Navigation: architecture, connectors, agents, API reference, Swiggy integration guide, evaluation, deployment. Custom domain. Public URL to share with Swiggy team, recruiters, restaurant clients. | feat: Mintlify docs website — public-facing CortexKitchen v2 documentation | All docs/ files | Planned | Medium | Anoushka |  | P7 | 0% | P7-03 | Docs site live at public URL; all 13 doc files render; search works; no broken links
P7 | P7-05 | dev -> main PR | Release | Sync Phase 7 to main — public release | Live production URL. README updated with live demo link + docs website link. Apply to jobs immediately. Update portfolio. | release: Phase 7 complete — CortexKitchen v2 live in production | README.md, anoushkavyas.vercel.app portfolio | Planned | Low | Anoushka |  | P7 | 0% | P7-04 | Full E2E on production URL; demo video recorded; portfolio updated

## Doc Strategy
CortexKitchen v2 — Documentation Strategy (Phase 6)
Doc File | What It Covers | Updated In (task ID) | Status
docs/CONNECTORS.md | BaseConnector interface, sync vs enrich, how to add new connector | P6-S01 — NEW | New
docs/SWIGGY_INTEGRATION.md | 22 tools used, parameter mappings, OAuth, rate limits, error handling | P6-D01 — updated P6-S01/S02/S03 | Updated (P6-S03 status ✅)
docs/ACTION_QUEUE.md | Action types, approval flow, non-idempotent execution patterns | P6-S13 — NEW | New
docs/DATA_SOURCES.md | All data sources, channels, sync frequency, source field values | P6-S03 — NEW | New
docs/PRODUCT_MODES.md | Ops / brief / live / voice mode specs, triggers, outputs | P6-S16 — NEW | New
docs/ARCHITECTURE.md | Connector layer, 11-node pipeline, action layer, product modes | P6-S01, P6-S10, P6-S13, P6-S16 | Updated (P6-S01/S02 done)
docs/AGENTS.md | 11 nodes incl. market_intel + dineout_manager, 5 assumption diffs | P6-S10, P6-S11, P6-S12 | Update
docs/APIS.md | All endpoints: brief, live, action queue, connector management | Each PR adding endpoint | Update
docs/DATA_MODEL.md | 6 new tables: connectors, platform_orders, action_queue, procurement_orders, market_snapshots, daily_briefs | P6-S02, P6-S13, P6-S16 | Updated (P6-S02 done)
docs/DECISIONS.md | D-019 connector pattern, D-020 Swiggy primary, D-021 action queue, D-022 product modes | P6-S01, P6-S03, P6-S13, P6-S16 | Updated (D-019 added P6-S01)
docs/ROADMAP.md | Phase 6 full plan, Phase 7 scoped | P6-S01, P6-D03 | Update
docs/EVALUATION.md | Eval criteria for market_intel + dineout_manager nodes | P6-S10, P6-S11 | Update
README.md + docs/README.md | Portfolio headline: CortexKitchen v2 Swiggy-native restaurant OS | P6-D03 | Update
CLAUDE.md | swiggy/ infra path, Swiggy docs URLs, env vars, BRANCH_DOCS pattern | P6-S01 | Created (P6-S01 done)
Mintlify docs website | Public-facing docs site — all docs/ files, custom domain | P7-04 — Phase 7 | Phase 7

## Git Practices
CortexKitchen — Git Branching Rules
Branch | Purpose | Rule | Current note
main | Stable milestone only | Only sync from dev when a phase milestone is safe/demo-ready | Phase 6 on dev (P6-S01/S02 merged). main has P5 + P6-00 series. Next main sync: end of Phase 6.
dev | Active integration branch | All merged feature work lands here first | Current base — P6-S04 (feature/agent-intelligence) IN PROGRESS; P6-S05/S06 blocked on Swiggy token
feature/... | All implementation and docs work | Create from latest dev, PR back to dev, then delete branch | Current style
Local cleanup | After merge | Delete remote + local feature branch, checkout dev, pull latest | Continue throughout project